## Definitions
Schedule Baseline - Definition: The approved version of the project schedule, which includes the planned start and finish dates for activities, milestones, and deliverables. Purpose: It serves as the benchmark against which actual project progress and performance are measured and controlled. Change control: Once approved, it can only be changed through formal change control procedures (e.g., via the change control board). Role in project management: It allows you to track schedule variance, forecast completion dates, and manage stakeholder expectations
.

## Processes & Knowledge Areas
Knowledge Areas | Project Management Process Groups
| Initiating | Planning | Executing | Monitoring & Controlling | Closing
Project Integration Management | Develop Project Charter | Develop Project Management Plan
Project Scope Management |  | Plan Scope Management Collect Requirements Define Scope Create WBS
Project IScheduke Management
Project Cost Management
Project Quality Management
Project IResource Management
Project Communications Management
Project Risk Management
Project Procurement Management
Project Stakeholder Management | Identify Stakeholders

## All ITTOs Summary
ID | Type | Name | Primary Process | Knowledge Areas | All Processes | Usage Count
I001 | Input | Business case | Develop Project Charter | Integration Management | Develop Project Charter | 1
I002 | Input | Benefits management plan | Develop Project Charter | Integration Management | Develop Project Charter | 1
I003 | Input | Agreements | Develop Project Charter | Integration Management, Stakeholder Management, Scope Management, Schedule Management, Cost Management, Risk Management, Resource Management, Procurement Management | Develop Project Charter, Identify Stakeholders, Collect Requirements, Develop Schedule, Determine Budget, Identify Risks, Plan Stakeholder Engagement, Monitor and Control Project Work, Control Resources, Control Procurements, Close Project or Phase | 11
I004 | Input | Enterprise environmental factors | Develop Project Charter | Integration Management, Stakeholder Management, Scope Management, Schedule Management, Cost Management, Quality Management, Resource Management, Communications Management, Risk Management, Procurement Management | Develop Project Charter, Identify Stakeholders, Develop Project Management Plan, Plan Scope Management, Collect Requirements, Define Scope, Create WBS, Plan Schedule Management, Define Activities, Sequence Activities, Estimate Activity Durations, Develop Schedule, Plan Cost Management, Estimate Costs, Determine Budget, Plan Quality Management, Plan Resource Management, Estimate Activity Resources, Plan Communications Management, Plan Risk Management, Identify Risks, Perform Qualitative Risk Analysis, Perform Quantitative Risk Analysis, Plan Risk Responses, Plan Procurement Management, Plan Stakeholder Engagement, Direct and Manage Project Work, Manage Project Knowledge, Acquire Resources, Develop Team, Manage Team, Manage Communications, Conduct Procurements, Manage Stakeholder Engagement, Monitor and Control Project Work, Perform Integrated Change Control, Control Quality, Monitor Communications, Control Procurements, Monitor Stakeholder Engagement | 40
I005 | Input | Organizational process assets | Develop Project Charter | Integration Management, Stakeholder Management, Scope Management, Schedule Management, Cost Management, Quality Management, Resource Management, Communications Management, Risk Management, Procurement Management | Develop Project Charter, Identify Stakeholders, Develop Project Management Plan, Plan Scope Management, Collect Requirements, Define Scope, Create WBS, Plan Schedule Management, Define Activities, Sequence Activities, Estimate Activity Durations, Develop Schedule, Plan Cost Management, Estimate Costs, Determine Budget, Plan Quality Management, Plan Resource Management, Estimate Activity Resources, Plan Communications Management, Plan Risk Management, Identify Risks, Perform Qualitative Risk Analysis, Perform Quantitative Risk Analysis, Plan Risk Responses, Plan Procurement Management, Plan Stakeholder Engagement, Direct and Manage Project Work, Manage Project Knowledge, Manage Quality, Acquire Resources, Develop Team, Manage Team, Manage Communications, Conduct Procurements, Manage Stakeholder Engagement, Monitor and Control Project Work, Perform Integrated Change Control, Control Scope, Control Schedule, Control Costs, Control Quality, Control Resources, Monitor Communications, Control Procurements, Monitor Stakeholder Engagement, Close Project or Phase | 46
I006 | Input | Project charter | Identify Stakeholders | Stakeholder Management, Integration Management, Scope Management, Schedule Management, Cost Management, Quality Management, Resource Management, Communications Management, Risk Management, Procurement Management | Identify Stakeholders, Develop Project Management Plan, Plan Scope Management, Collect Requirements, Define Scope, Plan Schedule Management, Plan Cost Management, Plan Quality Management, Plan Resource Management, Plan Communications Management, Plan Risk Management, Plan Procurement Management, Plan Stakeholder Engagement, Close Project or Phase | 14
I007 | Input | Business documents | Identify Stakeholders | Stakeholder Management, Scope Management, Cost Management, Procurement Management, Integration Management | Identify Stakeholders, Collect Requirements, Determine Budget, Plan Procurement Management, Close Project or Phase | 5
I008 | Input | Project management plan | Identify Stakeholders | Stakeholder Management, Scope Management, Schedule Management, Cost Management, Quality Management, Resource Management, Communications Management, Risk Management, Procurement Management, Integration Management | Identify Stakeholders, Plan Scope Management, Collect Requirements, Define Scope, Create WBS, Plan Schedule Management, Define Activities, Sequence Activities, Estimate Activity Durations, Develop Schedule, Plan Cost Management, Estimate Costs, Determine Budget, Plan Quality Management, Plan Resource Management, Estimate Activity Resources, Plan Communications Management, Plan Risk Management, Identify Risks, Perform Qualitative Risk Analysis, Perform Quantitative Risk Analysis, Plan Risk Responses, Plan Procurement Management, Plan Stakeholder Engagement, Direct and Manage Project Work, Manage Project Knowledge, Manage Quality, Acquire Resources, Develop Team, Manage Team, Manage Communications, Implement Risk Responses, Conduct Procurements, Manage Stakeholder Engagement, Monitor and Control Project Work, Perform Integrated Change Control, Validate Scope, Control Scope, Control Schedule, Control Costs, Control Quality, Control Resources, Monitor Communications, Monitor Risks, Control Procurements, Monitor Stakeholder Engagement, Close Project or Phase | 47
I009 | Input | Project documents | Identify Stakeholders | Stakeholder Management, Scope Management, Schedule Management, Cost Management, Quality Management, Resource Management, Communications Management, Risk Management, Procurement Management, Integration Management | Identify Stakeholders, Collect Requirements, Define Scope, Create WBS, Sequence Activities, Estimate Activity Durations, Develop Schedule, Estimate Costs, Determine Budget, Plan Quality Management, Plan Resource Management, Estimate Activity Resources, Plan Communications Management, Plan Risk Management, Identify Risks, Perform Qualitative Risk Analysis, Perform Quantitative Risk Analysis, Plan Risk Responses, Plan Procurement Management, Plan Stakeholder Engagement, Direct and Manage Project Work, Manage Project Knowledge, Manage Quality, Acquire Resources, Develop Team, Manage Team, Manage Communications, Implement Risk Responses, Conduct Procurements, Manage Stakeholder Engagement, Monitor and Control Project Work, Perform Integrated Change Control, Validate Scope, Control Scope, Control Schedule, Control Costs, Control Quality, Control Resources, Monitor Communications, Monitor Risks, Control Procurements, Monitor Stakeholder Engagement, Close Project or Phase | 43
I010 | Input | Outputs from other processes | Develop Project Management Plan | Integration Management | Develop Project Management Plan | 1
I011 | Input | Procurement documentation | Identify Risks | Risk Management, Procurement Management, Integration Management | Identify Risks, Conduct Procurements, Control Procurements, Close Project or Phase | 4
I012 | Input | Approved change requests | Direct and Manage Project Work | Integration Management, Quality Management, Procurement Management | Direct and Manage Project Work, Control Quality, Control Procurements | 3
I013 | Input | Deliverables | Manage Project Knowledge | Integration Management, Quality Management | Manage Project Knowledge, Control Quality | 2
I014 | Input | Work performance reports | Manage Team | Resource Management, Communications Management, Stakeholder Management, Integration Management, Risk Management, Procurement Management | Manage Team, Manage Communications, Manage Stakeholder Engagement, Perform Integrated Change Control, Monitor Risks, Control Procurements | 6
I015 | Input | Team performance assessments | Manage Team | Resource Management | Manage Team | 1
I016 | Input | Change requests | Implement Risk Responses | Risk Management, Integration Management | Implement Risk Responses, Perform Integrated Change Control | 2
I017 | Input | Seller proposals | Conduct Procurements | Procurement Management | Conduct Procurements | 1
I018 | Input | Work performance information | Monitor and Control Project Work | Integration Management | Monitor and Control Project Work | 1
I019 | Input | Verified deliverables | Validate Scope | Scope Management | Validate Scope | 1
I020 | Input | Work performance data | Validate Scope | Scope Management, Schedule Management, Cost Management, Quality Management, Resource Management, Communications Management, Risk Management, Stakeholder Management | Validate Scope, Control Scope, Control Schedule, Control Costs, Control Quality, Control Resources, Monitor Communications, Monitor Risks, Monitor Stakeholder Engagement | 9
I021 | Input | Project funding requirements | Control Costs | Cost Management | Control Costs | 1
I022 | Input | Accepted deliverables | Close Project or Phase | Integration Management | Close Project or Phase | 1
T001 | Tool/Technique | Expert judgment | Develop Project Charter | Integration Management, Stakeholder Management, Scope Management, Schedule Management, Cost Management, Quality Management, Resource Management, Communications Management, Risk Management, Procurement Management | Develop Project Charter, Identify Stakeholders, Develop Project Management Plan, Plan Scope Management, Collect Requirements, Define Scope, Create WBS, Plan Schedule Management, Define Activities, Estimate Activity Durations, Plan Cost Management, Estimate Costs, Determine Budget, Plan Quality Management, Plan Resource Management, Estimate Activity Resources, Plan Communications Management, Plan Risk Management, Identify Risks, Perform Qualitative Risk Analysis, Perform Quantitative Risk Analysis, Plan Risk Responses, Plan Procurement Management, Plan Stakeholder Engagement, Direct and Manage Project Work, Manage Project Knowledge, Implement Risk Responses, Conduct Procurements, Manage Stakeholder Engagement, Monitor and Control Project Work, Perform Integrated Change Control, Control Costs, Monitor Communications, Control Procurements, Monitor Stakeholder Engagement, Close Project or Phase | 36
T002 | Tool/Technique | Data gathering | Develop Project Charter | Integration Management, Stakeholder Management, Scope Management, Quality Management, Risk Management, Procurement Management | Develop Project Charter, Identify Stakeholders, Develop Project Management Plan, Collect Requirements, Plan Quality Management, Identify Risks, Perform Qualitative Risk Analysis, Perform Quantitative Risk Analysis, Plan Risk Responses, Plan Procurement Management, Plan Stakeholder Engagement, Manage Quality, Control Quality | 13
T003 | Tool/Technique | Interpersonal and team skills | Develop Project Charter | Integration Management, Stakeholder Management, Scope Management, Communications Management, Risk Management, Resource Management, Procurement Management | Develop Project Charter, Identify Stakeholders, Develop Project Management Plan, Collect Requirements, Define Scope, Plan Communications Management, Identify Risks, Perform Qualitative Risk Analysis, Perform Quantitative Risk Analysis, Plan Risk Responses, Manage Project Knowledge, Acquire Resources, Develop Team, Manage Team, Manage Communications, Implement Risk Responses, Conduct Procurements, Manage Stakeholder Engagement, Control Resources, Monitor Communications, Monitor Stakeholder Engagement | 21
T004 | Tool/Technique | Meetings | Develop Project Charter | Integration Management, Stakeholder Management, Scope Management, Schedule Management, Cost Management, Quality Management, Resource Management, Communications Management, Risk Management, Procurement Management | Develop Project Charter, Identify Stakeholders, Develop Project Management Plan, Plan Scope Management, Plan Schedule Management, Define Activities, Estimate Activity Durations, Plan Cost Management, Plan Quality Management, Plan Resource Management, Estimate Activity Resources, Plan Communications Management, Plan Risk Management, Identify Risks, Perform Qualitative Risk Analysis, Plan Procurement Management, Plan Stakeholder Engagement, Direct and Manage Project Work, Develop Team, Manage Communications, Manage Stakeholder Engagement, Monitor and Control Project Work, Perform Integrated Change Control, Control Quality, Monitor Communications, Monitor Risks, Monitor Stakeholder Engagement, Close Project or Phase | 28
T005 | Tool/Technique | Data analysis | Identify Stakeholders | Stakeholder Management, Scope Management, Schedule Management, Cost Management, Quality Management, Resource Management, Risk Management, Procurement Management, Integration Management | Identify Stakeholders, Plan Scope Management, Collect Requirements, Define Scope, Plan Schedule Management, Estimate Activity Durations, Develop Schedule, Plan Cost Management, Estimate Costs, Determine Budget, Plan Quality Management, Estimate Activity Resources, Plan Risk Management, Identify Risks, Perform Qualitative Risk Analysis, Perform Quantitative Risk Analysis, Plan Risk Responses, Plan Procurement Management, Plan Stakeholder Engagement, Manage Quality, Conduct Procurements, Monitor and Control Project Work, Perform Integrated Change Control, Control Scope, Control Schedule, Control Costs, Control Quality, Control Resources, Monitor Risks, Control Procurements, Monitor Stakeholder Engagement, Close Project or Phase | 32
T006 | Tool/Technique | Data representation | Identify Stakeholders | Stakeholder Management, Scope Management, Quality Management, Resource Management, Communications Management, Risk Management | Identify Stakeholders, Collect Requirements, Plan Quality Management, Plan Resource Management, Plan Communications Management, Perform Qualitative Risk Analysis, Plan Stakeholder Engagement, Manage Quality, Control Quality, Monitor Communications, Monitor Stakeholder Engagement | 11
T007 | Tool/Technique | Decision making | Collect Requirements | Scope Management, Schedule Management, Cost Management, Quality Management, Risk Management, Stakeholder Management, Resource Management, Integration Management | Collect Requirements, Define Scope, Estimate Activity Durations, Estimate Costs, Plan Quality Management, Plan Risk Responses, Plan Stakeholder Engagement, Manage Quality, Acquire Resources, Monitor and Control Project Work, Perform Integrated Change Control, Validate Scope, Monitor Stakeholder Engagement | 13
T008 | Tool/Technique | Context diagrams | Collect Requirements | Scope Management | Collect Requirements | 1
T009 | Tool/Technique | Prototypes | Collect Requirements | Scope Management | Collect Requirements | 1
T010 | Tool/Technique | Product analysis | Define Scope | Scope Management | Define Scope | 1
T011 | Tool/Technique | Decomposition | Create WBS | Scope Management, Schedule Management | Create WBS, Define Activities | 2
T012 | Tool/Technique | Rolling wave planning | Define Activities | Schedule Management | Define Activities | 1
T013 | Tool/Technique | Precedence diagramming method | Sequence Activities | Schedule Management | Sequence Activities | 1
T014 | Tool/Technique | Dependency determination and integration | Sequence Activities | Schedule Management | Sequence Activities | 1
T015 | Tool/Technique | Leads and lags | Sequence Activities | Schedule Management | Sequence Activities, Develop Schedule, Control Schedule | 3
T016 | Tool/Technique | Project management information system | Sequence Activities | Schedule Management, Cost Management, Resource Management, Integration Management, Communications Management, Risk Management, Stakeholder Management | Sequence Activities, Develop Schedule, Estimate Costs, Estimate Activity Resources, Direct and Manage Project Work, Manage Team, Manage Communications, Implement Risk Responses, Control Schedule, Control Costs, Control Resources, Monitor Communications, Monitor Stakeholder Engagement | 13
T017 | Tool/Technique | Analogous estimating | Estimate Activity Durations | Schedule Management, Cost Management, Resource Management | Estimate Activity Durations, Estimate Costs, Estimate Activity Resources | 3
T018 | Tool/Technique | Parametric estimating | Estimate Activity Durations | Schedule Management, Cost Management, Resource Management | Estimate Activity Durations, Estimate Costs, Estimate Activity Resources | 3
T019 | Tool/Technique | Three-point estimating | Estimate Activity Durations | Schedule Management, Cost Management | Estimate Activity Durations, Estimate Costs | 2
T020 | Tool/Technique | Bottom-up estimating | Estimate Activity Durations | Schedule Management, Cost Management, Resource Management | Estimate Activity Durations, Estimate Costs, Estimate Activity Resources | 3
T021 | Tool/Technique | Schedule network analysis | Develop Schedule | Schedule Management | Develop Schedule | 1
T022 | Tool/Technique | Critical path method | Develop Schedule | Schedule Management | Develop Schedule, Control Schedule | 2
T023 | Tool/Technique | Resource optimization | Develop Schedule | Schedule Management | Develop Schedule, Control Schedule | 2
T024 | Tool/Technique | Schedule compression | Develop Schedule | Schedule Management | Develop Schedule, Control Schedule | 2
T025 | Tool/Technique | Agile release planning | Develop Schedule | Schedule Management | Develop Schedule | 1
T026 | Tool/Technique | Cost aggregation | Determine Budget | Cost Management | Determine Budget | 1
T027 | Tool/Technique | Historical information review | Determine Budget | Cost Management | Determine Budget | 1
T028 | Tool/Technique | Funding limit reconciliation | Determine Budget | Cost Management | Determine Budget | 1
T029 | Tool/Technique | Financing | Determine Budget | Cost Management | Determine Budget | 1
T030 | Tool/Technique | Test and inspection planning | Plan Quality Management | Quality Management | Plan Quality Management | 1
T031 | Tool/Technique | Organizational theory | Plan Resource Management | Resource Management | Plan Resource Management | 1
T032 | Tool/Technique | Communication requirements analysis | Plan Communications Management | Communications Management | Plan Communications Management | 1
T033 | Tool/Technique | Communication technology | Plan Communications Management | Communications Management, Resource Management | Plan Communications Management, Develop Team, Manage Communications | 3
T034 | Tool/Technique | Communication models | Plan Communications Management | Communications Management | Plan Communications Management | 1
T035 | Tool/Technique | Communication methods | Plan Communications Management | Communications Management | Plan Communications Management, Manage Communications | 2
T036 | Tool/Technique | Prompt lists | Identify Risks | Risk Management | Identify Risks | 1
T037 | Tool/Technique | Risk categorization | Perform Qualitative Risk Analysis | Risk Management | Perform Qualitative Risk Analysis | 1
T038 | Tool/Technique | Representations of uncertainty | Perform Quantitative Risk Analysis | Risk Management | Perform Quantitative Risk Analysis | 1
T039 | Tool/Technique | Strategies for threats | Plan Risk Responses | Risk Management | Plan Risk Responses | 1
T040 | Tool/Technique | Strategies for opportunities | Plan Risk Responses | Risk Management | Plan Risk Responses | 1
T041 | Tool/Technique | Contingent response strategies | Plan Risk Responses | Risk Management | Plan Risk Responses | 1
T042 | Tool/Technique | Strategies for overall project risk | Plan Risk Responses | Risk Management | Plan Risk Responses | 1
T043 | Tool/Technique | Source selection analysis | Plan Procurement Management | Procurement Management | Plan Procurement Management | 1
T044 | Tool/Technique | Knowledge management | Manage Project Knowledge | Integration Management | Manage Project Knowledge | 1
T045 | Tool/Technique | Information management | Manage Project Knowledge | Integration Management | Manage Project Knowledge | 1
T046 | Tool/Technique | Audits | Manage Quality | Quality Management, Risk Management, Procurement Management | Manage Quality, Monitor Risks, Control Procurements | 3
T047 | Tool/Technique | Design for X | Manage Quality | Quality Management | Manage Quality | 1
T048 | Tool/Technique | Problem solving | Manage Quality | Quality Management, Resource Management | Manage Quality, Control Resources | 2
T049 | Tool/Technique | Quality improvement methods | Manage Quality | Quality Management | Manage Quality | 1
T050 | Tool/Technique | Pre-assignment | Acquire Resources | Resource Management | Acquire Resources | 1
T051 | Tool/Technique | Virtual teams | Acquire Resources | Resource Management | Acquire Resources, Develop Team | 2
T052 | Tool/Technique | Colocation | Develop Team | Resource Management | Develop Team | 1
T053 | Tool/Technique | Recognition and rewards | Develop Team | Resource Management | Develop Team | 1
T054 | Tool/Technique | Training | Develop Team | Resource Management | Develop Team | 1
T055 | Tool/Technique | Individual and team assessments | Develop Team | Resource Management | Develop Team | 1
T056 | Tool/Technique | Communication skills | Manage Communications | Communications Management, Stakeholder Management | Manage Communications, Manage Stakeholder Engagement | 2
T057 | Tool/Technique | Project reporting | Manage Communications | Communications Management | Manage Communications | 1
T058 | Tool/Technique | Advertising | Conduct Procurements | Procurement Management | Conduct Procurements | 1
T059 | Tool/Technique | Bidder conferences | Conduct Procurements | Procurement Management | Conduct Procurements | 1
T060 | Tool/Technique | Ground rules | Manage Stakeholder Engagement | Stakeholder Management | Manage Stakeholder Engagement | 1
T061 | Tool/Technique | Change control tools | Perform Integrated Change Control | Integration Management | Perform Integrated Change Control | 1
T062 | Tool/Technique | Inspection | Validate Scope | Scope Management, Quality Management, Procurement Management | Validate Scope, Control Quality, Control Procurements | 3
T063 | Tool/Technique | Variance analysis | Control Scope | Scope Management | Control Scope | 1
T064 | Tool/Technique | To-complete performance index | Control Costs | Cost Management | Control Costs | 1
T065 | Tool/Technique | Testing/product evaluations | Control Quality | Quality Management | Control Quality | 1
T066 | Tool/Technique | Claims administration | Control Procurements | Procurement Management | Control Procurements | 1
O001 | Output | Project charter | Develop Project Charter | Integration Management | Develop Project Charter | 1
O002 | Output | Assumption log | Develop Project Charter | Integration Management | Develop Project Charter | 1
O003 | Output | Stakeholder register | Identify Stakeholders | Stakeholder Management | Identify Stakeholders | 1
O004 | Output | Change requests | Identify Stakeholders | Stakeholder Management, Schedule Management, Risk Management, Procurement Management, Integration Management, Quality Management, Resource Management, Scope Management, Cost Management, Communications Management | Identify Stakeholders, Define Activities, Develop Schedule, Plan Risk Responses, Plan Procurement Management, Direct and Manage Project Work, Manage Quality, Acquire Resources, Develop Team, Manage Team, Implement Risk Responses, Conduct Procurements, Manage Stakeholder Engagement, Monitor and Control Project Work, Validate Scope, Control Scope, Control Schedule, Control Costs, Control Quality, Control Resources, Monitor Communications, Monitor Risks, Control Procurements, Monitor Stakeholder Engagement | 24
O005 | Output | Project management plan updates | Identify Stakeholders | Stakeholder Management, Schedule Management, Quality Management, Communications Management, Risk Management, Integration Management, Resource Management, Procurement Management, Scope Management, Cost Management | Identify Stakeholders, Define Activities, Develop Schedule, Plan Quality Management, Plan Communications Management, Plan Risk Responses, Direct and Manage Project Work, Manage Project Knowledge, Manage Quality, Acquire Resources, Develop Team, Manage Team, Manage Communications, Conduct Procurements, Manage Stakeholder Engagement, Monitor and Control Project Work, Perform Integrated Change Control, Control Scope, Control Schedule, Control Costs, Control Quality, Control Resources, Monitor Communications, Monitor Risks, Control Procurements, Monitor Stakeholder Engagement | 26
O006 | Output | Project documents updates | Identify Stakeholders | Stakeholder Management, Scope Management, Schedule Management, Cost Management, Quality Management, Resource Management, Communications Management, Risk Management, Procurement Management, Integration Management | Identify Stakeholders, Define Scope, Create WBS, Sequence Activities, Estimate Activity Durations, Develop Schedule, Estimate Costs, Determine Budget, Plan Quality Management, Plan Resource Management, Estimate Activity Resources, Plan Communications Management, Identify Risks, Perform Qualitative Risk Analysis, Perform Quantitative Risk Analysis, Plan Risk Responses, Plan Procurement Management, Direct and Manage Project Work, Manage Quality, Acquire Resources, Develop Team, Manage Team, Manage Communications, Implement Risk Responses, Conduct Procurements, Manage Stakeholder Engagement, Monitor and Control Project Work, Perform Integrated Change Control, Validate Scope, Control Scope, Control Schedule, Control Costs, Control Quality, Control Resources, Monitor Communications, Monitor Risks, Control Procurements, Monitor Stakeholder Engagement, Close Project or Phase | 39
O007 | Output | Project management plan | Develop Project Management Plan | Integration Management | Develop Project Management Plan | 1
O008 | Output | Scope management plan | Plan Scope Management | Scope Management | Plan Scope Management | 1
O009 | Output | Requirements management plan | Plan Scope Management | Scope Management | Plan Scope Management | 1
O010 | Output | Requirements documentation | Collect Requirements | Scope Management | Collect Requirements | 1
O011 | Output | Requirements traceability matrix | Collect Requirements | Scope Management | Collect Requirements | 1
O012 | Output | Project scope statement | Define Scope | Scope Management | Define Scope | 1
O013 | Output | Scope baseline | Create WBS | Scope Management | Create WBS | 1
O014 | Output | Schedule management plan | Plan Schedule Management | Schedule Management | Plan Schedule Management | 1
O015 | Output | Activity list | Define Activities | Schedule Management | Define Activities | 1
O016 | Output | Activity attributes | Define Activities | Schedule Management | Define Activities | 1
O017 | Output | Milestone list | Define Activities | Schedule Management | Define Activities | 1
O018 | Output | Project schedule network diagrams | Sequence Activities | Schedule Management | Sequence Activities | 1
O019 | Output | Duration estimates | Estimate Activity Durations | Schedule Management | Estimate Activity Durations | 1
O020 | Output | Basis of estimates | Estimate Activity Durations | Schedule Management, Cost Management, Resource Management | Estimate Activity Durations, Estimate Costs, Estimate Activity Resources | 3
O021 | Output | Schedule baseline | Develop Schedule | Schedule Management | Develop Schedule | 1
O022 | Output | Project schedule | Develop Schedule | Schedule Management | Develop Schedule | 1
O023 | Output | Schedule data | Develop Schedule | Schedule Management | Develop Schedule | 1
O024 | Output | Project calendars | Develop Schedule | Schedule Management | Develop Schedule | 1
O025 | Output | Cost management plan | Plan Cost Management | Cost Management | Plan Cost Management | 1
O026 | Output | Cost estimates | Estimate Costs | Cost Management | Estimate Costs | 1
O027 | Output | Cost baseline | Determine Budget | Cost Management | Determine Budget | 1
O028 | Output | Project funding requirements | Determine Budget | Cost Management | Determine Budget | 1
O029 | Output | Quality management plan | Plan Quality Management | Quality Management | Plan Quality Management | 1
O030 | Output | Quality metrics | Plan Quality Management | Quality Management | Plan Quality Management | 1
O031 | Output | Resource management plan | Plan Resource Management | Resource Management | Plan Resource Management | 1
O032 | Output | Team charter | Plan Resource Management | Resource Management | Plan Resource Management | 1
O033 | Output | Resource requirements | Estimate Activity Resources | Resource Management | Estimate Activity Resources | 1
O034 | Output | Resource breakdown structure | Estimate Activity Resources | Resource Management | Estimate Activity Resources | 1
O035 | Output | Communications management plan | Plan Communications Management | Communications Management | Plan Communications Management | 1
O036 | Output | Risk management plan | Plan Risk Management | Risk Management | Plan Risk Management | 1
O037 | Output | Risk register | Identify Risks | Risk Management | Identify Risks | 1
O038 | Output | Risk report | Identify Risks | Risk Management | Identify Risks | 1
O039 | Output | Procurement management plan | Plan Procurement Management | Procurement Management | Plan Procurement Management | 1
O040 | Output | Procurement strategy | Plan Procurement Management | Procurement Management | Plan Procurement Management | 1
O041 | Output | Bid documents | Plan Procurement Management | Procurement Management | Plan Procurement Management | 1
O042 | Output | Procurement statement of work | Plan Procurement Management | Procurement Management | Plan Procurement Management | 1
O043 | Output | Source selection criteria | Plan Procurement Management | Procurement Management | Plan Procurement Management | 1
O044 | Output | Make-or-buy decisions | Plan Procurement Management | Procurement Management | Plan Procurement Management | 1
O045 | Output | Independent cost estimates | Plan Procurement Management | Procurement Management | Plan Procurement Management | 1
O046 | Output | Organizational process assets updates | Plan Procurement Management | Procurement Management, Integration Management, Resource Management, Communications Management, Stakeholder Management | Plan Procurement Management, Direct and Manage Project Work, Manage Project Knowledge, Acquire Resources, Develop Team, Manage Communications, Conduct Procurements, Manage Stakeholder Engagement, Control Procurements, Close Project or Phase | 10
O047 | Output | Stakeholder engagement plan | Plan Stakeholder Engagement | Stakeholder Management | Plan Stakeholder Engagement | 1
O048 | Output | Deliverables | Direct and Manage Project Work | Integration Management | Direct and Manage Project Work | 1
O049 | Output | Work performance data | Direct and Manage Project Work | Integration Management | Direct and Manage Project Work | 1
O050 | Output | Issue log | Direct and Manage Project Work | Integration Management | Direct and Manage Project Work | 1
O051 | Output | Lessons learned register | Manage Project Knowledge | Integration Management | Manage Project Knowledge | 1
O052 | Output | Quality reports | Manage Quality | Quality Management | Manage Quality | 1
O053 | Output | Test and evaluation documents | Manage Quality | Quality Management | Manage Quality | 1
O054 | Output | Physical resource assignments | Acquire Resources | Resource Management | Acquire Resources | 1
O055 | Output | Project team assignments | Acquire Resources | Resource Management | Acquire Resources | 1
O056 | Output | Resource calendars | Acquire Resources | Resource Management | Acquire Resources | 1
O057 | Output | Enterprise environmental factors updates | Acquire Resources | Resource Management | Acquire Resources, Develop Team, Manage Team | 3
O058 | Output | Team performance assessments | Develop Team | Resource Management | Develop Team | 1
O059 | Output | Project communications | Manage Communications | Communications Management | Manage Communications | 1
O060 | Output | Selected sellers | Conduct Procurements | Procurement Management | Conduct Procurements | 1
O061 | Output | Agreements | Conduct Procurements | Procurement Management | Conduct Procurements | 1
O062 | Output | Work performance reports | Monitor and Control Project Work | Integration Management | Monitor and Control Project Work | 1
O063 | Output | Approved change requests | Perform Integrated Change Control | Integration Management | Perform Integrated Change Control | 1
O064 | Output | Accepted deliverables | Validate Scope | Scope Management | Validate Scope | 1
O065 | Output | Work performance information | Validate Scope | Scope Management, Schedule Management, Cost Management, Quality Management, Resource Management, Communications Management, Risk Management, Procurement Management, Stakeholder Management | Validate Scope, Control Scope, Control Schedule, Control Costs, Control Quality, Control Resources, Monitor Communications, Monitor Risks, Control Procurements, Monitor Stakeholder Engagement | 10
O066 | Output | Schedule forecasts | Control Schedule | Schedule Management | Control Schedule | 1
O067 | Output | Cost forecasts | Control Costs | Cost Management | Control Costs | 1
O068 | Output | Quality control measurements | Control Quality | Quality Management | Control Quality | 1
O069 | Output | Verified deliverables | Control Quality | Quality Management | Control Quality | 1
O070 | Output | Closed procurements | Control Procurements | Procurement Management | Control Procurements | 1
O071 | Output | Procurement documentation updates | Control Procurements | Procurement Management | Control Procurements | 1
O072 | Output | Final product/service/result transition | Close Project or Phase | Integration Management | Close Project or Phase | 1
O073 | Output | Final report | Close Project or Phase | Integration Management | Close Project or Phase | 1

## Process Reference
Process Group | Process Name | Knowledge Area | Input Count | Tool Count | Output Count
Initiating | Develop Project Charter | Integration Management | 5 | 4 | 2
Initiating | Identify Stakeholders | Stakeholder Management | 7 | 6 | 4
Planning | Develop Project Management Plan | Integration Management | 4 | 4 | 1
Planning | Plan Scope Management | Scope Management | 4 | 3 | 2
Planning | Collect Requirements | Scope Management | 7 | 8 | 2
Planning | Define Scope | Scope Management | 5 | 5 | 2
Planning | Create WBS | Scope Management | 4 | 2 | 2
Planning | Plan Schedule Management | Schedule Management | 4 | 3 | 1
Planning | Define Activities | Schedule Management | 3 | 4 | 5
Planning | Sequence Activities | Schedule Management | 4 | 4 | 2
Planning | Estimate Activity Durations | Schedule Management | 4 | 8 | 3
Planning | Develop Schedule | Schedule Management | 5 | 8 | 7
Planning | Plan Cost Management | Cost Management | 4 | 3 | 1
Planning | Estimate Costs | Cost Management | 4 | 8 | 3
Planning | Determine Budget | Cost Management | 6 | 6 | 3
Planning | Plan Quality Management | Quality Management | 5 | 7 | 4
Planning | Plan Resource Management | Resource Management | 5 | 4 | 3
Planning | Estimate Activity Resources | Resource Management | 4 | 7 | 4
Planning | Plan Communications Management | Communications Management | 5 | 8 | 3
Planning | Plan Risk Management | Risk Management | 5 | 3 | 1
Planning | Identify Risks | Risk Management | 6 | 6 | 3
Planning | Perform Qualitative Risk Analysis | Risk Management | 4 | 7 | 1
Planning | Perform Quantitative Risk Analysis | Risk Management | 4 | 5 | 1
Planning | Plan Risk Responses | Risk Management | 4 | 9 | 3
Planning | Plan Procurement Management | Procurement Management | 6 | 5 | 10
Planning | Plan Stakeholder Engagement | Stakeholder Management | 6 | 6 | 1
Executing | Direct and Manage Project Work | Integration Management | 5 | 3 | 7
Executing | Manage Project Knowledge | Integration Management | 5 | 4 | 3
Executing | Manage Quality | Quality Management | 3 | 8 | 5
Executing | Acquire Resources | Resource Management | 4 | 4 | 8
Executing | Develop Team | Resource Management | 4 | 8 | 6
Executing | Manage Team | Resource Management | 6 | 2 | 4
Executing | Manage Communications | Communications Management | 5 | 7 | 4
Executing | Implement Risk Responses | Risk Management | 3 | 3 | 2
Executing | Conduct Procurements | Procurement Management | 6 | 5 | 6
Executing | Manage Stakeholder Engagement | Stakeholder Management | 5 | 5 | 4
Monitoring & Controlling | Monitor and Control Project Work | Integration Management | 6 | 4 | 4
Monitoring & Controlling | Perform Integrated Change Control | Integration Management | 6 | 5 | 3
Monitoring & Controlling | Validate Scope | Scope Management | 4 | 2 | 4
Monitoring & Controlling | Control Scope | Scope Management | 4 | 2 | 4
Monitoring & Controlling | Control Schedule | Schedule Management | 4 | 6 | 5
Monitoring & Controlling | Control Costs | Cost Management | 5 | 4 | 5
Monitoring & Controlling | Control Quality | Quality Management | 7 | 6 | 6
Monitoring & Controlling | Control Resources | Resource Management | 5 | 4 | 4
Monitoring & Controlling | Monitor Communications | Communications Management | 5 | 5 | 4
Monitoring & Controlling | Monitor Risks | Risk Management | 4 | 3 | 4
Monitoring & Controlling | Control Procurements | Procurement Management | 8 | 5 | 7
Monitoring & Controlling | Monitor Stakeholder Engagement | Stakeholder Management | 5 | 7 | 4
Closing | Close Project or Phase | Integration Management | 8 | 3 | 4

## Inputs
Input ID | Input Name | Used In Processes | Knowledge Areas | Usage Count
I001 | Business case | Develop Project Charter | Integration Management | 1
I002 | Benefits management plan | Develop Project Charter | Integration Management | 1
I003 | Agreements | Develop Project Charter, Identify Stakeholders, Collect Requirements, Develop Schedule, Determine Budget, Identify Risks, Plan Stakeholder Engagement, Monitor and Control Project Work, Control Resources, Control Procurements, Close Project or Phase | Integration Management, Stakeholder Management, Scope Management, Schedule Management, Cost Management, Risk Management, Resource Management, Procurement Management | 11
I004 | Enterprise environmental factors | Develop Project Charter, Identify Stakeholders, Develop Project Management Plan, Plan Scope Management, Collect Requirements, Define Scope, Create WBS, Plan Schedule Management, Define Activities, Sequence Activities, Estimate Activity Durations, Develop Schedule, Plan Cost Management, Estimate Costs, Determine Budget, Plan Quality Management, Plan Resource Management, Estimate Activity Resources, Plan Communications Management, Plan Risk Management, Identify Risks, Perform Qualitative Risk Analysis, Perform Quantitative Risk Analysis, Plan Risk Responses, Plan Procurement Management, Plan Stakeholder Engagement, Direct and Manage Project Work, Manage Project Knowledge, Acquire Resources, Develop Team, Manage Team, Manage Communications, Conduct Procurements, Manage Stakeholder Engagement, Monitor and Control Project Work, Perform Integrated Change Control, Control Quality, Monitor Communications, Control Procurements, Monitor Stakeholder Engagement | Integration Management, Stakeholder Management, Scope Management, Schedule Management, Cost Management, Quality Management, Resource Management, Communications Management, Risk Management, Procurement Management | 40
I005 | Organizational process assets | Develop Project Charter, Identify Stakeholders, Develop Project Management Plan, Plan Scope Management, Collect Requirements, Define Scope, Create WBS, Plan Schedule Management, Define Activities, Sequence Activities, Estimate Activity Durations, Develop Schedule, Plan Cost Management, Estimate Costs, Determine Budget, Plan Quality Management, Plan Resource Management, Estimate Activity Resources, Plan Communications Management, Plan Risk Management, Identify Risks, Perform Qualitative Risk Analysis, Perform Quantitative Risk Analysis, Plan Risk Responses, Plan Procurement Management, Plan Stakeholder Engagement, Direct and Manage Project Work, Manage Project Knowledge, Manage Quality, Acquire Resources, Develop Team, Manage Team, Manage Communications, Conduct Procurements, Manage Stakeholder Engagement, Monitor and Control Project Work, Perform Integrated Change Control, Control Scope, Control Schedule, Control Costs, Control Quality, Control Resources, Monitor Communications, Control Procurements, Monitor Stakeholder Engagement, Close Project or Phase | Integration Management, Stakeholder Management, Scope Management, Schedule Management, Cost Management, Quality Management, Resource Management, Communications Management, Risk Management, Procurement Management | 46
I006 | Project charter | Identify Stakeholders, Develop Project Management Plan, Plan Scope Management, Collect Requirements, Define Scope, Plan Schedule Management, Plan Cost Management, Plan Quality Management, Plan Resource Management, Plan Communications Management, Plan Risk Management, Plan Procurement Management, Plan Stakeholder Engagement, Close Project or Phase | Stakeholder Management, Integration Management, Scope Management, Schedule Management, Cost Management, Quality Management, Resource Management, Communications Management, Risk Management, Procurement Management | 14
I007 | Business documents | Identify Stakeholders, Collect Requirements, Determine Budget, Plan Procurement Management, Close Project or Phase | Stakeholder Management, Scope Management, Cost Management, Procurement Management, Integration Management | 5
I008 | Project management plan | Identify Stakeholders, Plan Scope Management, Collect Requirements, Define Scope, Create WBS, Plan Schedule Management, Define Activities, Sequence Activities, Estimate Activity Durations, Develop Schedule, Plan Cost Management, Estimate Costs, Determine Budget, Plan Quality Management, Plan Resource Management, Estimate Activity Resources, Plan Communications Management, Plan Risk Management, Identify Risks, Perform Qualitative Risk Analysis, Perform Quantitative Risk Analysis, Plan Risk Responses, Plan Procurement Management, Plan Stakeholder Engagement, Direct and Manage Project Work, Manage Project Knowledge, Manage Quality, Acquire Resources, Develop Team, Manage Team, Manage Communications, Implement Risk Responses, Conduct Procurements, Manage Stakeholder Engagement, Monitor and Control Project Work, Perform Integrated Change Control, Validate Scope, Control Scope, Control Schedule, Control Costs, Control Quality, Control Resources, Monitor Communications, Monitor Risks, Control Procurements, Monitor Stakeholder Engagement, Close Project or Phase | Stakeholder Management, Scope Management, Schedule Management, Cost Management, Quality Management, Resource Management, Communications Management, Risk Management, Procurement Management, Integration Management | 47
I009 | Project documents | Identify Stakeholders, Collect Requirements, Define Scope, Create WBS, Sequence Activities, Estimate Activity Durations, Develop Schedule, Estimate Costs, Determine Budget, Plan Quality Management, Plan Resource Management, Estimate Activity Resources, Plan Communications Management, Plan Risk Management, Identify Risks, Perform Qualitative Risk Analysis, Perform Quantitative Risk Analysis, Plan Risk Responses, Plan Procurement Management, Plan Stakeholder Engagement, Direct and Manage Project Work, Manage Project Knowledge, Manage Quality, Acquire Resources, Develop Team, Manage Team, Manage Communications, Implement Risk Responses, Conduct Procurements, Manage Stakeholder Engagement, Monitor and Control Project Work, Perform Integrated Change Control, Validate Scope, Control Scope, Control Schedule, Control Costs, Control Quality, Control Resources, Monitor Communications, Monitor Risks, Control Procurements, Monitor Stakeholder Engagement, Close Project or Phase | Stakeholder Management, Scope Management, Schedule Management, Cost Management, Quality Management, Resource Management, Communications Management, Risk Management, Procurement Management, Integration Management | 43
I010 | Outputs from other processes | Develop Project Management Plan | Integration Management | 1
I011 | Procurement documentation | Identify Risks, Conduct Procurements, Control Procurements, Close Project or Phase | Risk Management, Procurement Management, Integration Management | 4
I012 | Approved change requests | Direct and Manage Project Work, Control Quality, Control Procurements | Integration Management, Quality Management, Procurement Management | 3
I013 | Deliverables | Manage Project Knowledge, Control Quality | Integration Management, Quality Management | 2
I014 | Work performance reports | Manage Team, Manage Communications, Manage Stakeholder Engagement, Perform Integrated Change Control, Monitor Risks, Control Procurements | Resource Management, Communications Management, Stakeholder Management, Integration Management, Risk Management, Procurement Management | 6
I015 | Team performance assessments | Manage Team | Resource Management | 1
I016 | Change requests | Implement Risk Responses, Perform Integrated Change Control | Risk Management, Integration Management | 2
I017 | Seller proposals | Conduct Procurements | Procurement Management | 1
I018 | Work performance information | Monitor and Control Project Work | Integration Management | 1
I019 | Verified deliverables | Validate Scope | Scope Management | 1
I020 | Work performance data | Validate Scope, Control Scope, Control Schedule, Control Costs, Control Quality, Control Resources, Monitor Communications, Monitor Risks, Monitor Stakeholder Engagement | Scope Management, Schedule Management, Cost Management, Quality Management, Resource Management, Communications Management, Risk Management, Stakeholder Management | 9
I021 | Project funding requirements | Control Costs | Cost Management | 1
I022 | Accepted deliverables | Close Project or Phase | Integration Management | 1

## Tools & Techniques
Tool ID | Tool/Technique Name | Used In Processes | Knowledge Areas | Usage Count
T001 | Expert judgment | Develop Project Charter, Identify Stakeholders, Develop Project Management Plan, Plan Scope Management, Collect Requirements, Define Scope, Create WBS, Plan Schedule Management, Define Activities, Estimate Activity Durations, Plan Cost Management, Estimate Costs, Determine Budget, Plan Quality Management, Plan Resource Management, Estimate Activity Resources, Plan Communications Management, Plan Risk Management, Identify Risks, Perform Qualitative Risk Analysis, Perform Quantitative Risk Analysis, Plan Risk Responses, Plan Procurement Management, Plan Stakeholder Engagement, Direct and Manage Project Work, Manage Project Knowledge, Implement Risk Responses, Conduct Procurements, Manage Stakeholder Engagement, Monitor and Control Project Work, Perform Integrated Change Control, Control Costs, Monitor Communications, Control Procurements, Monitor Stakeholder Engagement, Close Project or Phase | Integration Management, Stakeholder Management, Scope Management, Schedule Management, Cost Management, Quality Management, Resource Management, Communications Management, Risk Management, Procurement Management | 36
T002 | Data gathering | Develop Project Charter, Identify Stakeholders, Develop Project Management Plan, Collect Requirements, Plan Quality Management, Identify Risks, Perform Qualitative Risk Analysis, Perform Quantitative Risk Analysis, Plan Risk Responses, Plan Procurement Management, Plan Stakeholder Engagement, Manage Quality, Control Quality | Integration Management, Stakeholder Management, Scope Management, Quality Management, Risk Management, Procurement Management | 13
T003 | Interpersonal and team skills | Develop Project Charter, Identify Stakeholders, Develop Project Management Plan, Collect Requirements, Define Scope, Plan Communications Management, Identify Risks, Perform Qualitative Risk Analysis, Perform Quantitative Risk Analysis, Plan Risk Responses, Manage Project Knowledge, Acquire Resources, Develop Team, Manage Team, Manage Communications, Implement Risk Responses, Conduct Procurements, Manage Stakeholder Engagement, Control Resources, Monitor Communications, Monitor Stakeholder Engagement | Integration Management, Stakeholder Management, Scope Management, Communications Management, Risk Management, Resource Management, Procurement Management | 21
T004 | Meetings | Develop Project Charter, Identify Stakeholders, Develop Project Management Plan, Plan Scope Management, Plan Schedule Management, Define Activities, Estimate Activity Durations, Plan Cost Management, Plan Quality Management, Plan Resource Management, Estimate Activity Resources, Plan Communications Management, Plan Risk Management, Identify Risks, Perform Qualitative Risk Analysis, Plan Procurement Management, Plan Stakeholder Engagement, Direct and Manage Project Work, Develop Team, Manage Communications, Manage Stakeholder Engagement, Monitor and Control Project Work, Perform Integrated Change Control, Control Quality, Monitor Communications, Monitor Risks, Monitor Stakeholder Engagement, Close Project or Phase | Integration Management, Stakeholder Management, Scope Management, Schedule Management, Cost Management, Quality Management, Resource Management, Communications Management, Risk Management, Procurement Management | 28
T005 | Data analysis | Identify Stakeholders, Plan Scope Management, Collect Requirements, Define Scope, Plan Schedule Management, Estimate Activity Durations, Develop Schedule, Plan Cost Management, Estimate Costs, Determine Budget, Plan Quality Management, Estimate Activity Resources, Plan Risk Management, Identify Risks, Perform Qualitative Risk Analysis, Perform Quantitative Risk Analysis, Plan Risk Responses, Plan Procurement Management, Plan Stakeholder Engagement, Manage Quality, Conduct Procurements, Monitor and Control Project Work, Perform Integrated Change Control, Control Scope, Control Schedule, Control Costs, Control Quality, Control Resources, Monitor Risks, Control Procurements, Monitor Stakeholder Engagement, Close Project or Phase | Stakeholder Management, Scope Management, Schedule Management, Cost Management, Quality Management, Resource Management, Risk Management, Procurement Management, Integration Management | 32
T006 | Data representation | Identify Stakeholders, Collect Requirements, Plan Quality Management, Plan Resource Management, Plan Communications Management, Perform Qualitative Risk Analysis, Plan Stakeholder Engagement, Manage Quality, Control Quality, Monitor Communications, Monitor Stakeholder Engagement | Stakeholder Management, Scope Management, Quality Management, Resource Management, Communications Management, Risk Management | 11
T007 | Decision making | Collect Requirements, Define Scope, Estimate Activity Durations, Estimate Costs, Plan Quality Management, Plan Risk Responses, Plan Stakeholder Engagement, Manage Quality, Acquire Resources, Monitor and Control Project Work, Perform Integrated Change Control, Validate Scope, Monitor Stakeholder Engagement | Scope Management, Schedule Management, Cost Management, Quality Management, Risk Management, Stakeholder Management, Resource Management, Integration Management | 13
T008 | Context diagrams | Collect Requirements | Scope Management | 1
T009 | Prototypes | Collect Requirements | Scope Management | 1
T010 | Product analysis | Define Scope | Scope Management | 1
T011 | Decomposition | Create WBS, Define Activities | Scope Management, Schedule Management | 2
T012 | Rolling wave planning | Define Activities | Schedule Management | 1
T013 | Precedence diagramming method | Sequence Activities | Schedule Management | 1
T014 | Dependency determination and integration | Sequence Activities | Schedule Management | 1
T015 | Leads and lags | Sequence Activities, Develop Schedule, Control Schedule | Schedule Management | 3
T016 | Project management information system | Sequence Activities, Develop Schedule, Estimate Costs, Estimate Activity Resources, Direct and Manage Project Work, Manage Team, Manage Communications, Implement Risk Responses, Control Schedule, Control Costs, Control Resources, Monitor Communications, Monitor Stakeholder Engagement | Schedule Management, Cost Management, Resource Management, Integration Management, Communications Management, Risk Management, Stakeholder Management | 13
T017 | Analogous estimating | Estimate Activity Durations, Estimate Costs, Estimate Activity Resources | Schedule Management, Cost Management, Resource Management | 3
T018 | Parametric estimating | Estimate Activity Durations, Estimate Costs, Estimate Activity Resources | Schedule Management, Cost Management, Resource Management | 3
T019 | Three-point estimating | Estimate Activity Durations, Estimate Costs | Schedule Management, Cost Management | 2
T020 | Bottom-up estimating | Estimate Activity Durations, Estimate Costs, Estimate Activity Resources | Schedule Management, Cost Management, Resource Management | 3
T021 | Schedule network analysis | Develop Schedule | Schedule Management | 1
T022 | Critical path method | Develop Schedule, Control Schedule | Schedule Management | 2
T023 | Resource optimization | Develop Schedule, Control Schedule | Schedule Management | 2
T024 | Schedule compression | Develop Schedule, Control Schedule | Schedule Management | 2
T025 | Agile release planning | Develop Schedule | Schedule Management | 1
T026 | Cost aggregation | Determine Budget | Cost Management | 1
T027 | Historical information review | Determine Budget | Cost Management | 1
T028 | Funding limit reconciliation | Determine Budget | Cost Management | 1
T029 | Financing | Determine Budget | Cost Management | 1
T030 | Test and inspection planning | Plan Quality Management | Quality Management | 1
T031 | Organizational theory | Plan Resource Management | Resource Management | 1
T032 | Communication requirements analysis | Plan Communications Management | Communications Management | 1
T033 | Communication technology | Plan Communications Management, Develop Team, Manage Communications | Communications Management, Resource Management | 3
T034 | Communication models | Plan Communications Management | Communications Management | 1
T035 | Communication methods | Plan Communications Management, Manage Communications | Communications Management | 2
T036 | Prompt lists | Identify Risks | Risk Management | 1
T037 | Risk categorization | Perform Qualitative Risk Analysis | Risk Management | 1
T038 | Representations of uncertainty | Perform Quantitative Risk Analysis | Risk Management | 1
T039 | Strategies for threats | Plan Risk Responses | Risk Management | 1
T040 | Strategies for opportunities | Plan Risk Responses | Risk Management | 1
T041 | Contingent response strategies | Plan Risk Responses | Risk Management | 1
T042 | Strategies for overall project risk | Plan Risk Responses | Risk Management | 1
T043 | Source selection analysis | Plan Procurement Management | Procurement Management | 1
T044 | Knowledge management | Manage Project Knowledge | Integration Management | 1
T045 | Information management | Manage Project Knowledge | Integration Management | 1
T046 | Audits | Manage Quality, Monitor Risks, Control Procurements | Quality Management, Risk Management, Procurement Management | 3
T047 | Design for X | Manage Quality | Quality Management | 1
T048 | Problem solving | Manage Quality, Control Resources | Quality Management, Resource Management | 2
T049 | Quality improvement methods | Manage Quality | Quality Management | 1
T050 | Pre-assignment | Acquire Resources | Resource Management | 1
T051 | Virtual teams | Acquire Resources, Develop Team | Resource Management | 2
T052 | Colocation | Develop Team | Resource Management | 1
T053 | Recognition and rewards | Develop Team | Resource Management | 1
T054 | Training | Develop Team | Resource Management | 1
T055 | Individual and team assessments | Develop Team | Resource Management | 1
T056 | Communication skills | Manage Communications, Manage Stakeholder Engagement | Communications Management, Stakeholder Management | 2
T057 | Project reporting | Manage Communications | Communications Management | 1
T058 | Advertising | Conduct Procurements | Procurement Management | 1
T059 | Bidder conferences | Conduct Procurements | Procurement Management | 1
T060 | Ground rules | Manage Stakeholder Engagement | Stakeholder Management | 1
T061 | Change control tools | Perform Integrated Change Control | Integration Management | 1
T062 | Inspection | Validate Scope, Control Quality, Control Procurements | Scope Management, Quality Management, Procurement Management | 3
T063 | Variance analysis | Control Scope | Scope Management | 1
T064 | To-complete performance index | Control Costs | Cost Management | 1
T065 | Testing/product evaluations | Control Quality | Quality Management | 1
T066 | Claims administration | Control Procurements | Procurement Management | 1

## Outputs
Output ID | Output Name | Produced By Processes | Knowledge Areas | Usage Count
O001 | Project charter | Develop Project Charter | Integration Management | 1 | The project charter is a document that officially authorizes the project to get started. Here are a few things thje project charter includes Project justification Name of project manager Assignment of authority to the pm Signature of the sponsor or others authorizing the project
O002 | Assumption log | Develop Project Charter | Integration Management | 1 | Log of all the assumptions and constraints that are identified throughout the project. List of things expected to be true and things that may constrain the project. Continuously updated.
O003 | Stakeholder register | Identify Stakeholders | Stakeholder Management | 1 | Document identifying all project stakeholders, their interests, involvement levels, and influence on the project
O004 | Change requests | Identify Stakeholders, Define Activities, Develop Schedule, Plan Risk Responses, Plan Procurement Management, Direct and Manage Project Work, Manage Quality, Acquire Resources, Develop Team, Manage Team, Implement Risk Responses, Conduct Procurements, Manage Stakeholder Engagement, Monitor and Control Project Work, Validate Scope, Control Scope, Control Schedule, Control Costs, Control Quality, Control Resources, Monitor Communications, Monitor Risks, Control Procurements, Monitor Stakeholder Engagement | Stakeholder Management, Schedule Management, Risk Management, Procurement Management, Integration Management, Quality Management, Resource Management, Scope Management, Cost Management, Communications Management | 24 | Formal proposals to modify any project document, deliverable, or baseline
O005 | Project management plan updates | Identify Stakeholders, Define Activities, Develop Schedule, Plan Quality Management, Plan Communications Management, Plan Risk Responses, Direct and Manage Project Work, Manage Project Knowledge, Manage Quality, Acquire Resources, Develop Team, Manage Team, Manage Communications, Conduct Procurements, Manage Stakeholder Engagement, Monitor and Control Project Work, Perform Integrated Change Control, Control Scope, Control Schedule, Control Costs, Control Quality, Control Resources, Monitor Communications, Monitor Risks, Control Procurements, Monitor Stakeholder Engagement | Stakeholder Management, Schedule Management, Quality Management, Communications Management, Risk Management, Integration Management, Resource Management, Procurement Management, Scope Management, Cost Management | 26 | Revisions to any component of the project management plan
O006 | Project documents updates | Identify Stakeholders, Define Scope, Create WBS, Sequence Activities, Estimate Activity Durations, Develop Schedule, Estimate Costs, Determine Budget, Plan Quality Management, Plan Resource Management, Estimate Activity Resources, Plan Communications Management, Identify Risks, Perform Qualitative Risk Analysis, Perform Quantitative Risk Analysis, Plan Risk Responses, Plan Procurement Management, Direct and Manage Project Work, Manage Quality, Acquire Resources, Develop Team, Manage Team, Manage Communications, Implement Risk Responses, Conduct Procurements, Manage Stakeholder Engagement, Monitor and Control Project Work, Perform Integrated Change Control, Validate Scope, Control Scope, Control Schedule, Control Costs, Control Quality, Control Resources, Monitor Communications, Monitor Risks, Control Procurements, Monitor Stakeholder Engagement, Close Project or Phase | Stakeholder Management, Scope Management, Schedule Management, Cost Management, Quality Management, Resource Management, Communications Management, Risk Management, Procurement Management, Integration Management | 39 | Revisions to any project documents outside the project management plan
O007 | Project management plan | Develop Project Management Plan | Integration Management | 1 | Comprehensive document that defines how the project is executed, monitored, controlled, and closed
O008 | Scope management plan | Plan Scope Management | Scope Management | 1 | Component of the project management plan that describes how the project scope will be defined, developed, monitored, controlled, and validated
O009 | Requirements management plan | Plan Scope Management | Scope Management | 1 | Component of the project management plan that describes how requirements will be analyzed
O010 | Requirements documentation | Collect Requirements | Scope Management | 1 | Description of how individual requirements meet the business need for the project
O011 | Requirements traceability matrix | Collect Requirements | Scope Management | 1 | Grid that links product requirements from their origin to the deliverables that satisfy them
O012 | Project scope statement | Define Scope | Scope Management | 1 | Description of the project scope, major deliverables, assumptions, and constraints
O013 | Scope baseline | Create WBS | Scope Management | 1 | Approved version of the scope statement, work breakdown structure (WBS), and WBS dictionary
O014 | Schedule management plan | Plan Schedule Management | Schedule Management | 1 | Component of the project management plan that establishes the criteria and activities for developing, monitoring, and controlling the schedule
O015 | Activity list | Define Activities | Schedule Management | 1 | Comprehensive list including all schedule activities required on the project
O016 | Activity attributes | Define Activities | Schedule Management | 1 | Multiple attributes associated with each schedule activity that can be included within the activity list
O017 | Milestone list | Define Activities | Schedule Management | 1 | List identifying all project milestones and indicates whether the milestone is mandatory or optional
O018 | Project schedule network diagrams | Sequence Activities | Schedule Management | 1 | Graphical representation of the logical relationships among the project schedule activities
O019 | Duration estimates | Estimate Activity Durations | Schedule Management | 1 | Quantitative assessments of the likely number of work periods required to complete an activity
O020 | Basis of estimates | Estimate Activity Durations, Estimate Costs, Estimate Activity Resources | Schedule Management, Cost Management, Resource Management | 3 | Supporting documentation outlining the details used in establishing project estimates
O021 | Schedule baseline | Develop Schedule | Schedule Management | 1 | Approved version of a schedule model that can be changed using formal change control procedures
O022 | Project schedule | Develop Schedule | Schedule Management | 1 | Output of a schedule model that presents linked activities with planned dates, durations, milestones, and resources
O023 | Schedule data | Develop Schedule | Schedule Management | 1 | Collection of information for describing and controlling the schedule
O024 | Project calendars | Develop Schedule | Schedule Management | 1 | Calendar that identifies working days and shifts available for scheduled activities
O025 | Cost management plan | Plan Cost Management | Cost Management | 1 | Component of the project management plan that describes how project costs will be planned, structured, and controlled
O026 | Cost estimates | Estimate Costs | Cost Management | 1 | Quantitative assessment of the likely costs for resources required to complete the activity
O027 | Cost baseline | Determine Budget | Cost Management | 1 | Approved version of the time-phased project budget, excluding management reserves
O028 | Project funding requirements | Determine Budget | Cost Management | 1 | Forecast project costs to be funded for each time period
O029 | Quality management plan | Plan Quality Management | Quality Management | 1 | Component of the project management plan that describes how an organization's quality policies will be implemented
O030 | Quality metrics | Plan Quality Management | Quality Management | 1 | Description of a project or product attribute and how to measure it
O031 | Resource management plan | Plan Resource Management | Resource Management | 1 | Component of the project management plan that describes how project resources are acquired, allocated, monitored, and controlled
O032 | Team charter | Plan Resource Management | Resource Management | 1 | Document that establishes the team values, agreements, and operating guidelines for the team
O033 | Resource requirements | Estimate Activity Resources | Resource Management | 1 | Types and quantities of resources required for each activity in a work package
O034 | Resource breakdown structure | Estimate Activity Resources | Resource Management | 1 | Hierarchical representation of resources by category and type
O035 | Communications management plan | Plan Communications Management | Communications Management | 1 | Component of the project management plan that describes how project communications will be planned, structured, and monitored
O036 | Risk management plan | Plan Risk Management | Risk Management | 1 | Component of the project management plan that describes how risk management activities will be structured and performed
O037 | Risk register | Identify Risks | Risk Management | 1 | Document in which the results of risk analysis and risk response planning are recorded
O038 | Risk report | Identify Risks | Risk Management | 1 | Project document developed progressively throughout the risk management process that summarizes individual risks and overall risk
O039 | Procurement management plan | Plan Procurement Management | Procurement Management | 1 | Component of the project management plan that describes how a team will acquire goods and services from outside the performing organization
O040 | Procurement strategy | Plan Procurement Management | Procurement Management | 1 | Approach to determine the project delivery method and the type of legally binding agreement(s)
O041 | Bid documents | Plan Procurement Management | Procurement Management | 1 | Documents used to solicit information, quotations, or proposals from prospective sellers
O042 | Procurement statement of work | Plan Procurement Management | Procurement Management | 1 | Description of the procurement item in sufficient detail to allow prospective sellers to determine if they can provide the products
O043 | Source selection criteria | Plan Procurement Management | Procurement Management | 1 | Set of attributes desired by the buyer which a seller is required to meet or exceed to be selected for a contract
O044 | Make-or-buy decisions | Plan Procurement Management | Procurement Management | 1 | Decisions made regarding the external purchase or internal manufacture of the product
O045 | Independent cost estimates | Plan Procurement Management | Procurement Management | 1 | Cost estimate prepared by an outside professional estimator to serve as a benchmark
O046 | Organizational process assets updates | Plan Procurement Management, Direct and Manage Project Work, Manage Project Knowledge, Acquire Resources, Develop Team, Manage Communications, Conduct Procurements, Manage Stakeholder Engagement, Control Procurements, Close Project or Phase | Procurement Management, Integration Management, Resource Management, Communications Management, Stakeholder Management | 10 | Updates to any or all organizational process assets involved in the project
O047 | Stakeholder engagement plan | Plan Stakeholder Engagement | Stakeholder Management | 1 | Component of the project management plan that identifies the strategies to effectively engage stakeholders
O048 | Deliverables | Direct and Manage Project Work | Integration Management | 1 | Any unique and verifiable product
O049 | Work performance data | Direct and Manage Project Work | Integration Management | 1 | Raw observations and measurements identified during activities being performed to carry out the project work
O050 | Issue log | Direct and Manage Project Work | Integration Management | 1 | Project document used to record and monitor information on active issues
O051 | Lessons learned register | Manage Project Knowledge | Integration Management | 1 | Project document used to record knowledge gained during a project
O052 | Quality reports | Manage Quality | Quality Management | 1 | Project documents that include quality management issues, recommendations for corrective actions, and summary of findings
O053 | Test and evaluation documents | Manage Quality | Quality Management | 1 | Project documents that describe the activities used to determine if the product meets the quality requirements
O054 | Physical resource assignments | Acquire Resources | Resource Management | 1 | Documentation of which physical resources are assigned to which activities
O055 | Project team assignments | Acquire Resources | Resource Management | 1 | Documentation of team member assignments to the project
O056 | Resource calendars | Acquire Resources | Resource Management | 1 | Calendar that identifies the working days and shifts upon which each specific resource is available
O057 | Enterprise environmental factors updates | Acquire Resources, Develop Team, Manage Team | Resource Management | 3 | Updates to any or all enterprise environmental factors that influence the project
O058 | Team performance assessments | Develop Team | Resource Management | 1 | Evaluation of a project team's effectiveness
O059 | Project communications | Manage Communications | Communications Management | 1 | Information that is created and distributed to project stakeholders
O060 | Selected sellers | Conduct Procurements | Procurement Management | 1 | Sellers that have been selected to provide a contracted service or product
O061 | Agreements | Conduct Procurements | Procurement Management | 1 | Document or communication that defines the initial intentions for a project
O062 | Work performance reports | Monitor and Control Project Work | Integration Management | 1 | Physical or electronic representation of work performance information compiled in project documents
O063 | Approved change requests | Perform Integrated Change Control | Integration Management | 1 | Change requests processed through the integrated change control process and approved
O064 | Accepted deliverables | Validate Scope | Scope Management | 1 | Products
O065 | Work performance information | Validate Scope, Control Scope, Control Schedule, Control Costs, Control Quality, Control Resources, Monitor Communications, Monitor Risks, Control Procurements, Monitor Stakeholder Engagement | Scope Management, Schedule Management, Cost Management, Quality Management, Resource Management, Communications Management, Risk Management, Procurement Management, Stakeholder Management | 10 | Performance data collected from various controlling processes
O066 | Schedule forecasts | Control Schedule | Schedule Management | 1 | Estimates or predictions of conditions and events in the project's future based on information and knowledge available at the time
O067 | Cost forecasts | Control Costs | Cost Management | 1 | Calculated EAC (Estimate at Completion) value or a bottom-up EAC value
O068 | Quality control measurements | Control Quality | Quality Management | 1 | Results of quality control activities that are fed back to the quality assurance process
O069 | Verified deliverables | Control Quality | Quality Management | 1 | Completed project deliverables that have been checked and confirmed for correctness through the Control Quality process
O070 | Closed procurements | Control Procurements | Procurement Management | 1 | Completed and settled contract where all agreements are finalized and closed
O071 | Procurement documentation updates | Control Procurements | Procurement Management | 1 | Updates to procurement documents as a result of the procurement process
O072 | Final product/service/result transition | Close Project or Phase | Integration Management | 1 | Transfer of the final product
O073 | Final report | Close Project or Phase | Integration Management | 1 | Document that provides a summary of the project performance

## Sheet1
Output,Definition
Document identifying all project stakeholders, their interests, involvement levels, and influence on the project
Formal proposals to modify any project document, deliverable, or baseline
Revisions to any component of the project management plan
Revisions to any project documents outside the project management plan
Comprehensive document that defines how the project is executed, monitored, controlled, and closed
Component of the project management plan that describes how the project scope will be defined, developed, monitored, controlled, and validated
Component of the project management plan that describes how requirements will be analyzed
Description of how individual requirements meet the business need for the project
Grid that links product requirements from their origin to the deliverables that satisfy them
Description of the project scope, major deliverables, assumptions, and constraints
Approved version of the scope statement, work breakdown structure (WBS), and WBS dictionary
Component of the project management plan that establishes the criteria and activities for developing, monitoring, and controlling the schedule
Comprehensive list including all schedule activities required on the project
Multiple attributes associated with each schedule activity that can be included within the activity list
List identifying all project milestones and indicates whether the milestone is mandatory or optional
Graphical representation of the logical relationships among the project schedule activities
Quantitative assessments of the likely number of work periods required to complete an activity
Supporting documentation outlining the details used in establishing project estimates
Approved version of a schedule model that can be changed using formal change control procedures
Output of a schedule model that presents linked activities with planned dates, durations, milestones, and resources
Collection of information for describing and controlling the schedule
Calendar that identifies working days and shifts available for scheduled activities
Component of the project management plan that describes how project costs will be planned, structured, and controlled
Quantitative assessment of the likely costs for resources required to complete the activity
Approved version of the time-phased project budget, excluding management reserves
Forecast project costs to be funded for each time period
Component of the project management plan that describes how an organization's quality policies will be implemented
Description of a project or product attribute and how to measure it
Component of the project management plan that describes how project resources are acquired, allocated, monitored, and controlled
Document that establishes the team values, agreements, and operating guidelines for the team
Types and quantities of resources required for each activity in a work package
Hierarchical representation of resources by category and type
Component of the project management plan that describes how project communications will be planned, structured, and monitored
Component of the project management plan that describes how risk management activities will be structured and performed
Document in which the results of risk analysis and risk response planning are recorded
Project document developed progressively throughout the risk management process that summarizes individual risks and overall risk
Component of the project management plan that describes how a team will acquire goods and services from outside the performing organization
Approach to determine the project delivery method and the type of legally binding agreement(s)
Documents used to solicit information, quotations, or proposals from prospective sellers
Description of the procurement item in sufficient detail to allow prospective sellers to determine if they can provide the products
Set of attributes desired by the buyer which a seller is required to meet or exceed to be selected for a contract
Decisions made regarding the external purchase or internal manufacture of the product
Cost estimate prepared by an outside professional estimator to serve as a benchmark
Updates to any or all organizational process assets involved in the project
Component of the project management plan that identifies the strategies to effectively engage stakeholders
Any unique and verifiable product
Raw observations and measurements identified during activities being performed to carry out the project work
Project document used to record and monitor information on active issues
Project document used to record knowledge gained during a project
Project documents that include quality management issues, recommendations for corrective actions, and summary of findings
Project documents that describe the activities used to determine if the product meets the quality requirements
Documentation of which physical resources are assigned to which activities
Documentation of team member assignments to the project
Calendar that identifies the working days and shifts upon which each specific resource is available
Updates to any or all enterprise environmental factors that influence the project
Evaluation of a project team's effectiveness
Information that is created and distributed to project stakeholders
Sellers that have been selected to provide a contracted service or product
Document or communication that defines the initial intentions for a project
Physical or electronic representation of work performance information compiled in project documents
Change requests processed through the integrated change control process and approved
Products
Performance data collected from various controlling processes
Estimates or predictions of conditions and events in the project's future based on information and knowledge available at the time
Calculated EAC (Estimate at Completion) value or a bottom-up EAC value
Results of quality control activities that are fed back to the quality assurance process
Completed project deliverables that have been checked and confirmed for correctness through the Control Quality process
Completed and settled contract where all agreements are finalized and closed
Updates to procurement documents as a result of the procurement process
Transfer of the final product
Document that provides a summary of the project performance

## Diagrams
Affinity Diagram - A diagram that shows large numbers of ideas, data or information classified into groups for review and analysis. - Organize ideas and group related cocepts - Identify patterns and connections between ideas - Risk categorization - Root cause analysis - Stakeholder mapping - Process improvement - Identify gaps, collaboration Network Diagram - Showd activity dependencies and logical sequence - Shows critical path Fishbone/Ishikawa Diagram - Root cause analysis for problems or risks - Quality management, problem solving and risl identification Pareto Chart (80/20 Rule) - Most significant porblems or causes - Quality control, resource focus 🎯 Diagram Selection by Purpose: For Planning: WBS - Scope definition Network Diagram - Schedule planning Gantt Chart - Timeline visualization For Risk Management: Fishbone - Root cause analysis Risk Matrix - Risk prioritization Tornado - Sensitivity analysis For Stakeholder Management: Power/Interest Grid - Engagement strategy RACI Matrix - Role clarity For Quality Management: Pareto Chart - Problem prioritization Control Chart - Performance monitoring Process Flow - Workflow mapping For Team Management: RACI Matrix - Responsibility assignment Burndown Chart - Progress tracking

## CH2 Terms
Questions | Answers
1 | a
2 | a
3 | b
4 | a | Portfolio management
5 | c | Weak matrix
6 | d
7 | b
8 | a
9 | b
10 | a
11 | a
12 | a
13 | a
14 | c
15 | b
16 | d
17 | a
18 | c
19 | a
20 | d
21 | d
22
23
24
25
26
27
28
29
30

## CH3 Processes
Questions | Answers
1 | d
2 | a
3 | b
4 | b
5 | c
6 | b
7 | a
8 | a
9 | b
10 | a
11 | c
12 | a
13 | d
14 | b
15 | d
16 | a
17 | a
18 | b
19 | d
20 | c
21 |  | 85%
22
23
24
25
26
27
28
29
30

## CH4 Agile
Questions | Answers
1 | c
2 | a
3 | b
4 | d
5 | a
6 | c
7 | b
8 | b
9 | a
10 | c
11 | a
12 | b
13 | b
14 | b
15 | c
16 | a
17 | c
18 | d
19 | d
20 | b
21 | b
22 | b
23 | d
24 | c
25 | c | Changiong of team members should not be allowed during during an iteration as it willl change velocity
26 | d
27 | b
28 | a
29 | a
30 | b | On an agile project, the goal is to have as much stakehollder engagement as possiblle, which willl lead to more satisfied stakeholders.

## CH5 IntegrationMGMT
Questions | Answers
1 | d
2 | d
3 | d
4 | d
5 | b
6 | a
7 | c
8 | d
9 | b
10 | a
11 | a
12 | c
13 | a
14 | c
15 | a
16 | b
17 | b
18 | a
19 | d
20 | d
21 | c
22 | b
23 | a
24 | a
25 |  | 79.17%
26
27
28
29
30

## CH6 Project Scope Management
Questions | Answers
1 | d
2 | a
3 | c
4 | d
5 | a
6 | d
7 | c
8 | d
9 | c
10 | b
11 | c
12 | d
13 | c
14 | a
15 | d
16 | c
17 | b
18 | c
19 | d
20 | d
21 | c
22 | a
23 | b
24 | c
25 | b
26 | d
27 | d
28 | c
29 | c
30 | a
a
| Score | 74.19%

## CH7 Project Schedule Management
Questions | Answers
1 | a
2 | a
3 | d
4 | a
5 | b
6 | b
7 | a
8 | b
9 | b
10 | d
11 | d
12 | b
13 | b
14 | c
15 | d
16 | a
17 | d
18 | a
19 | c
20 | d
21 | a
22 | c
23 | d
24 | a
25 | c
26 | a
27 | c
28 | b
29
30
| Score | 67.86%

## CH8 Project Cost Management
Questions | Answers
1 | b
2 | d
3 | a
4 | c
5 | d
6 | b
7 | c
8 | d
9 | d
10 | c
11 | b
12 | a
13 | b
14 | a
15 | c
16 | d
17 | a
18 | c
19 | b
20 | c
21 | d
22 | c
23 | b
24 | d
25 | c
26 | c
27 | d
28
29
30
| Score | 66.67%

## Interactive Dashboard
Process | Knowledge Area | Process Group | ITTO Type | ITTO ID | ITTO Name | Usage Count
Develop Project Charter | Integration Management | Initiating | Input | I001 | Business case | 1
Develop Project Charter | Integration Management | Initiating | Input | I002 | Benefits management plan | 1
Develop Project Charter | Integration Management | Initiating | Input | I003 | Agreements | 11
Develop Project Charter | Integration Management | Initiating | Input | I004 | Enterprise environmental factors | 40
Develop Project Charter | Integration Management | Initiating | Input | I005 | Organizational process assets | 46
Develop Project Charter | Integration Management | Initiating | Tool/Technique | T001 | Expert judgment | 36
Develop Project Charter | Integration Management | Initiating | Tool/Technique | T002 | Data gathering | 13
Develop Project Charter | Integration Management | Initiating | Tool/Technique | T003 | Interpersonal and team skills | 21
Develop Project Charter | Integration Management | Initiating | Tool/Technique | T004 | Meetings | 28
Develop Project Charter | Integration Management | Initiating | Output | O001 | Project charter | 1
Develop Project Charter | Integration Management | Initiating | Output | O002 | Assumption log | 1
Identify Stakeholders | Stakeholder Management | Initiating | Input | I006 | Project charter | 14
Identify Stakeholders | Stakeholder Management | Initiating | Input | I007 | Business documents | 5
Identify Stakeholders | Stakeholder Management | Initiating | Input | I008 | Project management plan | 47
Identify Stakeholders | Stakeholder Management | Initiating | Input | I009 | Project documents | 43
Identify Stakeholders | Stakeholder Management | Initiating | Input | I003 | Agreements | 11
Identify Stakeholders | Stakeholder Management | Initiating | Input | I004 | Enterprise environmental factors | 40
Identify Stakeholders | Stakeholder Management | Initiating | Input | I005 | Organizational process assets | 46
Identify Stakeholders | Stakeholder Management | Initiating | Tool/Technique | T001 | Expert judgment | 36
Identify Stakeholders | Stakeholder Management | Initiating | Tool/Technique | T002 | Data gathering | 13
Identify Stakeholders | Stakeholder Management | Initiating | Tool/Technique | T005 | Data analysis | 32
Identify Stakeholders | Stakeholder Management | Initiating | Tool/Technique | T006 | Data representation | 11
Identify Stakeholders | Stakeholder Management | Initiating | Tool/Technique | T003 | Interpersonal and team skills | 21
Identify Stakeholders | Stakeholder Management | Initiating | Tool/Technique | T004 | Meetings | 28
Identify Stakeholders | Stakeholder Management | Initiating | Output | O003 | Stakeholder register | 1
Identify Stakeholders | Stakeholder Management | Initiating | Output | O004 | Change requests | 24
Identify Stakeholders | Stakeholder Management | Initiating | Output | O005 | Project management plan updates | 26
Identify Stakeholders | Stakeholder Management | Initiating | Output | O006 | Project documents updates | 39
Develop Project Management Plan | Integration Management | Planning | Input | I006 | Project charter | 14
Develop Project Management Plan | Integration Management | Planning | Input | I010 | Outputs from other processes | 1
Develop Project Management Plan | Integration Management | Planning | Input | I004 | Enterprise environmental factors | 40
Develop Project Management Plan | Integration Management | Planning | Input | I005 | Organizational process assets | 46
Develop Project Management Plan | Integration Management | Planning | Tool/Technique | T001 | Expert judgment | 36
Develop Project Management Plan | Integration Management | Planning | Tool/Technique | T002 | Data gathering | 13
Develop Project Management Plan | Integration Management | Planning | Tool/Technique | T003 | Interpersonal and team skills | 21
Develop Project Management Plan | Integration Management | Planning | Tool/Technique | T004 | Meetings | 28
Develop Project Management Plan | Integration Management | Planning | Output | O007 | Project management plan | 1
Plan Scope Management | Scope Management | Planning | Input | I006 | Project charter | 14
Plan Scope Management | Scope Management | Planning | Input | I008 | Project management plan | 47
Plan Scope Management | Scope Management | Planning | Input | I004 | Enterprise environmental factors | 40
Plan Scope Management | Scope Management | Planning | Input | I005 | Organizational process assets | 46
Plan Scope Management | Scope Management | Planning | Tool/Technique | T001 | Expert judgment | 36
Plan Scope Management | Scope Management | Planning | Tool/Technique | T005 | Data analysis | 32
Plan Scope Management | Scope Management | Planning | Tool/Technique | T004 | Meetings | 28
Plan Scope Management | Scope Management | Planning | Output | O008 | Scope management plan | 1
Plan Scope Management | Scope Management | Planning | Output | O009 | Requirements management plan | 1
Collect Requirements | Scope Management | Planning | Input | I006 | Project charter | 14
Collect Requirements | Scope Management | Planning | Input | I008 | Project management plan | 47
Collect Requirements | Scope Management | Planning | Input | I009 | Project documents | 43
Collect Requirements | Scope Management | Planning | Input | I007 | Business documents | 5
Collect Requirements | Scope Management | Planning | Input | I003 | Agreements | 11
Collect Requirements | Scope Management | Planning | Input | I004 | Enterprise environmental factors | 40
Collect Requirements | Scope Management | Planning | Input | I005 | Organizational process assets | 46
Collect Requirements | Scope Management | Planning | Tool/Technique | T001 | Expert judgment | 36
Collect Requirements | Scope Management | Planning | Tool/Technique | T002 | Data gathering | 13
Collect Requirements | Scope Management | Planning | Tool/Technique | T005 | Data analysis | 32
Collect Requirements | Scope Management | Planning | Tool/Technique | T007 | Decision making | 13
Collect Requirements | Scope Management | Planning | Tool/Technique | T006 | Data representation | 11
Collect Requirements | Scope Management | Planning | Tool/Technique | T003 | Interpersonal and team skills | 21
Collect Requirements | Scope Management | Planning | Tool/Technique | T008 | Context diagrams | 1
Collect Requirements | Scope Management | Planning | Tool/Technique | T009 | Prototypes | 1
Collect Requirements | Scope Management | Planning | Output | O010 | Requirements documentation | 1
Collect Requirements | Scope Management | Planning | Output | O011 | Requirements traceability matrix | 1
Define Scope | Scope Management | Planning | Input | I006 | Project charter | 14
Define Scope | Scope Management | Planning | Input | I008 | Project management plan | 47
Define Scope | Scope Management | Planning | Input | I009 | Project documents | 43
Define Scope | Scope Management | Planning | Input | I004 | Enterprise environmental factors | 40
Define Scope | Scope Management | Planning | Input | I005 | Organizational process assets | 46
Define Scope | Scope Management | Planning | Tool/Technique | T001 | Expert judgment | 36
Define Scope | Scope Management | Planning | Tool/Technique | T005 | Data analysis | 32
Define Scope | Scope Management | Planning | Tool/Technique | T007 | Decision making | 13
Define Scope | Scope Management | Planning | Tool/Technique | T003 | Interpersonal and team skills | 21
Define Scope | Scope Management | Planning | Tool/Technique | T010 | Product analysis | 1
Define Scope | Scope Management | Planning | Output | O012 | Project scope statement | 1
Define Scope | Scope Management | Planning | Output | O006 | Project documents updates | 39
Create WBS | Scope Management | Planning | Input | I008 | Project management plan | 47
Create WBS | Scope Management | Planning | Input | I009 | Project documents | 43
Create WBS | Scope Management | Planning | Input | I004 | Enterprise environmental factors | 40
Create WBS | Scope Management | Planning | Input | I005 | Organizational process assets | 46
Create WBS | Scope Management | Planning | Tool/Technique | T001 | Expert judgment | 36
Create WBS | Scope Management | Planning | Tool/Technique | T011 | Decomposition | 2
Create WBS | Scope Management | Planning | Output | O013 | Scope baseline | 1
Create WBS | Scope Management | Planning | Output | O006 | Project documents updates | 39
Plan Schedule Management | Schedule Management | Planning | Input | I006 | Project charter | 14
Plan Schedule Management | Schedule Management | Planning | Input | I008 | Project management plan | 47
Plan Schedule Management | Schedule Management | Planning | Input | I004 | Enterprise environmental factors | 40
Plan Schedule Management | Schedule Management | Planning | Input | I005 | Organizational process assets | 46
Plan Schedule Management | Schedule Management | Planning | Tool/Technique | T001 | Expert judgment | 36
Plan Schedule Management | Schedule Management | Planning | Tool/Technique | T005 | Data analysis | 32
Plan Schedule Management | Schedule Management | Planning | Tool/Technique | T004 | Meetings | 28
Plan Schedule Management | Schedule Management | Planning | Output | O014 | Schedule management plan | 1
Define Activities | Schedule Management | Planning | Input | I008 | Project management plan | 47
Define Activities | Schedule Management | Planning | Input | I004 | Enterprise environmental factors | 40
Define Activities | Schedule Management | Planning | Input | I005 | Organizational process assets | 46
Define Activities | Schedule Management | Planning | Tool/Technique | T001 | Expert judgment | 36
Define Activities | Schedule Management | Planning | Tool/Technique | T011 | Decomposition | 2
Define Activities | Schedule Management | Planning | Tool/Technique | T012 | Rolling wave planning | 1
Define Activities | Schedule Management | Planning | Tool/Technique | T004 | Meetings | 28
Define Activities | Schedule Management | Planning | Output | O015 | Activity list | 1
Define Activities | Schedule Management | Planning | Output | O016 | Activity attributes | 1
Define Activities | Schedule Management | Planning | Output | O017 | Milestone list | 1
Define Activities | Schedule Management | Planning | Output | O004 | Change requests | 24
Define Activities | Schedule Management | Planning | Output | O005 | Project management plan updates | 26
Sequence Activities | Schedule Management | Planning | Input | I008 | Project management plan | 47
Sequence Activities | Schedule Management | Planning | Input | I009 | Project documents | 43
Sequence Activities | Schedule Management | Planning | Input | I004 | Enterprise environmental factors | 40
Sequence Activities | Schedule Management | Planning | Input | I005 | Organizational process assets | 46
Sequence Activities | Schedule Management | Planning | Tool/Technique | T013 | Precedence diagramming method | 1
Sequence Activities | Schedule Management | Planning | Tool/Technique | T014 | Dependency determination and integration | 1
Sequence Activities | Schedule Management | Planning | Tool/Technique | T015 | Leads and lags | 3
Sequence Activities | Schedule Management | Planning | Tool/Technique | T016 | Project management information system | 13
Sequence Activities | Schedule Management | Planning | Output | O018 | Project schedule network diagrams | 1
Sequence Activities | Schedule Management | Planning | Output | O006 | Project documents updates | 39
Estimate Activity Durations | Schedule Management | Planning | Input | I008 | Project management plan | 47
Estimate Activity Durations | Schedule Management | Planning | Input | I009 | Project documents | 43
Estimate Activity Durations | Schedule Management | Planning | Input | I004 | Enterprise environmental factors | 40
Estimate Activity Durations | Schedule Management | Planning | Input | I005 | Organizational process assets | 46
Estimate Activity Durations | Schedule Management | Planning | Tool/Technique | T001 | Expert judgment | 36
Estimate Activity Durations | Schedule Management | Planning | Tool/Technique | T017 | Analogous estimating | 3
Estimate Activity Durations | Schedule Management | Planning | Tool/Technique | T018 | Parametric estimating | 3
Estimate Activity Durations | Schedule Management | Planning | Tool/Technique | T019 | Three-point estimating | 2
Estimate Activity Durations | Schedule Management | Planning | Tool/Technique | T020 | Bottom-up estimating | 3
Estimate Activity Durations | Schedule Management | Planning | Tool/Technique | T005 | Data analysis | 32
Estimate Activity Durations | Schedule Management | Planning | Tool/Technique | T007 | Decision making | 13
Estimate Activity Durations | Schedule Management | Planning | Tool/Technique | T004 | Meetings | 28
Estimate Activity Durations | Schedule Management | Planning | Output | O019 | Duration estimates | 1
Estimate Activity Durations | Schedule Management | Planning | Output | O020 | Basis of estimates | 3
Estimate Activity Durations | Schedule Management | Planning | Output | O006 | Project documents updates | 39
Develop Schedule | Schedule Management | Planning | Input | I008 | Project management plan | 47
Develop Schedule | Schedule Management | Planning | Input | I009 | Project documents | 43
Develop Schedule | Schedule Management | Planning | Input | I003 | Agreements | 11
Develop Schedule | Schedule Management | Planning | Input | I004 | Enterprise environmental factors | 40
Develop Schedule | Schedule Management | Planning | Input | I005 | Organizational process assets | 46
Develop Schedule | Schedule Management | Planning | Tool/Technique | T021 | Schedule network analysis | 1
Develop Schedule | Schedule Management | Planning | Tool/Technique | T022 | Critical path method | 2
Develop Schedule | Schedule Management | Planning | Tool/Technique | T023 | Resource optimization | 2
Develop Schedule | Schedule Management | Planning | Tool/Technique | T005 | Data analysis | 32
Develop Schedule | Schedule Management | Planning | Tool/Technique | T015 | Leads and lags | 3
Develop Schedule | Schedule Management | Planning | Tool/Technique | T024 | Schedule compression | 2
Develop Schedule | Schedule Management | Planning | Tool/Technique | T016 | Project management information system | 13
Develop Schedule | Schedule Management | Planning | Tool/Technique | T025 | Agile release planning | 1
Develop Schedule | Schedule Management | Planning | Output | O021 | Schedule baseline | 1
Develop Schedule | Schedule Management | Planning | Output | O022 | Project schedule | 1
Develop Schedule | Schedule Management | Planning | Output | O023 | Schedule data | 1
Develop Schedule | Schedule Management | Planning | Output | O024 | Project calendars | 1
Develop Schedule | Schedule Management | Planning | Output | O004 | Change requests | 24
Develop Schedule | Schedule Management | Planning | Output | O005 | Project management plan updates | 26
Develop Schedule | Schedule Management | Planning | Output | O006 | Project documents updates | 39
Plan Cost Management | Cost Management | Planning | Input | I006 | Project charter | 14
Plan Cost Management | Cost Management | Planning | Input | I008 | Project management plan | 47
Plan Cost Management | Cost Management | Planning | Input | I004 | Enterprise environmental factors | 40
Plan Cost Management | Cost Management | Planning | Input | I005 | Organizational process assets | 46
Plan Cost Management | Cost Management | Planning | Tool/Technique | T001 | Expert judgment | 36
Plan Cost Management | Cost Management | Planning | Tool/Technique | T005 | Data analysis | 32
Plan Cost Management | Cost Management | Planning | Tool/Technique | T004 | Meetings | 28
Plan Cost Management | Cost Management | Planning | Output | O025 | Cost management plan | 1
Estimate Costs | Cost Management | Planning | Input | I008 | Project management plan | 47
Estimate Costs | Cost Management | Planning | Input | I009 | Project documents | 43
Estimate Costs | Cost Management | Planning | Input | I004 | Enterprise environmental factors | 40
Estimate Costs | Cost Management | Planning | Input | I005 | Organizational process assets | 46
Estimate Costs | Cost Management | Planning | Tool/Technique | T001 | Expert judgment | 36
Estimate Costs | Cost Management | Planning | Tool/Technique | T017 | Analogous estimating | 3
Estimate Costs | Cost Management | Planning | Tool/Technique | T018 | Parametric estimating | 3
Estimate Costs | Cost Management | Planning | Tool/Technique | T020 | Bottom-up estimating | 3
Estimate Costs | Cost Management | Planning | Tool/Technique | T019 | Three-point estimating | 2
Estimate Costs | Cost Management | Planning | Tool/Technique | T005 | Data analysis | 32
Estimate Costs | Cost Management | Planning | Tool/Technique | T016 | Project management information system | 13
Estimate Costs | Cost Management | Planning | Tool/Technique | T007 | Decision making | 13
Estimate Costs | Cost Management | Planning | Output | O026 | Cost estimates | 1
Estimate Costs | Cost Management | Planning | Output | O020 | Basis of estimates | 3
Estimate Costs | Cost Management | Planning | Output | O006 | Project documents updates | 39
Determine Budget | Cost Management | Planning | Input | I008 | Project management plan | 47
Determine Budget | Cost Management | Planning | Input | I009 | Project documents | 43
Determine Budget | Cost Management | Planning | Input | I007 | Business documents | 5
Determine Budget | Cost Management | Planning | Input | I003 | Agreements | 11
Determine Budget | Cost Management | Planning | Input | I004 | Enterprise environmental factors | 40
Determine Budget | Cost Management | Planning | Input | I005 | Organizational process assets | 46
Determine Budget | Cost Management | Planning | Tool/Technique | T001 | Expert judgment | 36
Determine Budget | Cost Management | Planning | Tool/Technique | T026 | Cost aggregation | 1
Determine Budget | Cost Management | Planning | Tool/Technique | T005 | Data analysis | 32
Determine Budget | Cost Management | Planning | Tool/Technique | T027 | Historical information review | 1
Determine Budget | Cost Management | Planning | Tool/Technique | T028 | Funding limit reconciliation | 1
Determine Budget | Cost Management | Planning | Tool/Technique | T029 | Financing | 1
Determine Budget | Cost Management | Planning | Output | O027 | Cost baseline | 1
Determine Budget | Cost Management | Planning | Output | O028 | Project funding requirements | 1
Determine Budget | Cost Management | Planning | Output | O006 | Project documents updates | 39
Plan Quality Management | Quality Management | Planning | Input | I006 | Project charter | 14
Plan Quality Management | Quality Management | Planning | Input | I008 | Project management plan | 47
Plan Quality Management | Quality Management | Planning | Input | I009 | Project documents | 43
Plan Quality Management | Quality Management | Planning | Input | I004 | Enterprise environmental factors | 40
Plan Quality Management | Quality Management | Planning | Input | I005 | Organizational process assets | 46
Plan Quality Management | Quality Management | Planning | Tool/Technique | T001 | Expert judgment | 36
Plan Quality Management | Quality Management | Planning | Tool/Technique | T002 | Data gathering | 13
Plan Quality Management | Quality Management | Planning | Tool/Technique | T005 | Data analysis | 32
Plan Quality Management | Quality Management | Planning | Tool/Technique | T007 | Decision making | 13
Plan Quality Management | Quality Management | Planning | Tool/Technique | T006 | Data representation | 11
Plan Quality Management | Quality Management | Planning | Tool/Technique | T030 | Test and inspection planning | 1
Plan Quality Management | Quality Management | Planning | Tool/Technique | T004 | Meetings | 28
Plan Quality Management | Quality Management | Planning | Output | O029 | Quality management plan | 1
Plan Quality Management | Quality Management | Planning | Output | O030 | Quality metrics | 1
Plan Quality Management | Quality Management | Planning | Output | O005 | Project management plan updates | 26
Plan Quality Management | Quality Management | Planning | Output | O006 | Project documents updates | 39
Plan Resource Management | Resource Management | Planning | Input | I006 | Project charter | 14
Plan Resource Management | Resource Management | Planning | Input | I008 | Project management plan | 47
Plan Resource Management | Resource Management | Planning | Input | I009 | Project documents | 43
Plan Resource Management | Resource Management | Planning | Input | I004 | Enterprise environmental factors | 40
Plan Resource Management | Resource Management | Planning | Input | I005 | Organizational process assets | 46
Plan Resource Management | Resource Management | Planning | Tool/Technique | T001 | Expert judgment | 36
Plan Resource Management | Resource Management | Planning | Tool/Technique | T006 | Data representation | 11
Plan Resource Management | Resource Management | Planning | Tool/Technique | T031 | Organizational theory | 1
Plan Resource Management | Resource Management | Planning | Tool/Technique | T004 | Meetings | 28
Plan Resource Management | Resource Management | Planning | Output | O031 | Resource management plan | 1
Plan Resource Management | Resource Management | Planning | Output | O032 | Team charter | 1
Plan Resource Management | Resource Management | Planning | Output | O006 | Project documents updates | 39
Estimate Activity Resources | Resource Management | Planning | Input | I008 | Project management plan | 47
Estimate Activity Resources | Resource Management | Planning | Input | I009 | Project documents | 43
Estimate Activity Resources | Resource Management | Planning | Input | I004 | Enterprise environmental factors | 40
Estimate Activity Resources | Resource Management | Planning | Input | I005 | Organizational process assets | 46
Estimate Activity Resources | Resource Management | Planning | Tool/Technique | T001 | Expert judgment | 36
Estimate Activity Resources | Resource Management | Planning | Tool/Technique | T020 | Bottom-up estimating | 3
Estimate Activity Resources | Resource Management | Planning | Tool/Technique | T017 | Analogous estimating | 3
Estimate Activity Resources | Resource Management | Planning | Tool/Technique | T018 | Parametric estimating | 3
Estimate Activity Resources | Resource Management | Planning | Tool/Technique | T005 | Data analysis | 32
Estimate Activity Resources | Resource Management | Planning | Tool/Technique | T016 | Project management information system | 13
Estimate Activity Resources | Resource Management | Planning | Tool/Technique | T004 | Meetings | 28
Estimate Activity Resources | Resource Management | Planning | Output | O033 | Resource requirements | 1
Estimate Activity Resources | Resource Management | Planning | Output | O020 | Basis of estimates | 3
Estimate Activity Resources | Resource Management | Planning | Output | O034 | Resource breakdown structure | 1
Estimate Activity Resources | Resource Management | Planning | Output | O006 | Project documents updates | 39
Plan Communications Management | Communications Management | Planning | Input | I006 | Project charter | 14
Plan Communications Management | Communications Management | Planning | Input | I008 | Project management plan | 47
Plan Communications Management | Communications Management | Planning | Input | I009 | Project documents | 43
Plan Communications Management | Communications Management | Planning | Input | I004 | Enterprise environmental factors | 40
Plan Communications Management | Communications Management | Planning | Input | I005 | Organizational process assets | 46
Plan Communications Management | Communications Management | Planning | Tool/Technique | T001 | Expert judgment | 36
Plan Communications Management | Communications Management | Planning | Tool/Technique | T032 | Communication requirements analysis | 1
Plan Communications Management | Communications Management | Planning | Tool/Technique | T033 | Communication technology | 3
Plan Communications Management | Communications Management | Planning | Tool/Technique | T034 | Communication models | 1
Plan Communications Management | Communications Management | Planning | Tool/Technique | T035 | Communication methods | 2
Plan Communications Management | Communications Management | Planning | Tool/Technique | T003 | Interpersonal and team skills | 21
Plan Communications Management | Communications Management | Planning | Tool/Technique | T006 | Data representation | 11
Plan Communications Management | Communications Management | Planning | Tool/Technique | T004 | Meetings | 28
Plan Communications Management | Communications Management | Planning | Output | O035 | Communications management plan | 1
Plan Communications Management | Communications Management | Planning | Output | O005 | Project management plan updates | 26
Plan Communications Management | Communications Management | Planning | Output | O006 | Project documents updates | 39
Plan Risk Management | Risk Management | Planning | Input | I006 | Project charter | 14
Plan Risk Management | Risk Management | Planning | Input | I008 | Project management plan | 47
Plan Risk Management | Risk Management | Planning | Input | I009 | Project documents | 43
Plan Risk Management | Risk Management | Planning | Input | I004 | Enterprise environmental factors | 40
Plan Risk Management | Risk Management | Planning | Input | I005 | Organizational process assets | 46
Plan Risk Management | Risk Management | Planning | Tool/Technique | T001 | Expert judgment | 36
Plan Risk Management | Risk Management | Planning | Tool/Technique | T005 | Data analysis | 32
Plan Risk Management | Risk Management | Planning | Tool/Technique | T004 | Meetings | 28
Plan Risk Management | Risk Management | Planning | Output | O036 | Risk management plan | 1
Identify Risks | Risk Management | Planning | Input | I008 | Project management plan | 47
Identify Risks | Risk Management | Planning | Input | I009 | Project documents | 43
Identify Risks | Risk Management | Planning | Input | I003 | Agreements | 11
Identify Risks | Risk Management | Planning | Input | I011 | Procurement documentation | 4
Identify Risks | Risk Management | Planning | Input | I004 | Enterprise environmental factors | 40
Identify Risks | Risk Management | Planning | Input | I005 | Organizational process assets | 46
Identify Risks | Risk Management | Planning | Tool/Technique | T001 | Expert judgment | 36
Identify Risks | Risk Management | Planning | Tool/Technique | T002 | Data gathering | 13
Identify Risks | Risk Management | Planning | Tool/Technique | T005 | Data analysis | 32
Identify Risks | Risk Management | Planning | Tool/Technique | T003 | Interpersonal and team skills | 21
Identify Risks | Risk Management | Planning | Tool/Technique | T036 | Prompt lists | 1
Identify Risks | Risk Management | Planning | Tool/Technique | T004 | Meetings | 28
Identify Risks | Risk Management | Planning | Output | O037 | Risk register | 1
Identify Risks | Risk Management | Planning | Output | O038 | Risk report | 1
Identify Risks | Risk Management | Planning | Output | O006 | Project documents updates | 39
Perform Qualitative Risk Analysis | Risk Management | Planning | Input | I008 | Project management plan | 47
Perform Qualitative Risk Analysis | Risk Management | Planning | Input | I009 | Project documents | 43
Perform Qualitative Risk Analysis | Risk Management | Planning | Input | I004 | Enterprise environmental factors | 40
Perform Qualitative Risk Analysis | Risk Management | Planning | Input | I005 | Organizational process assets | 46
Perform Qualitative Risk Analysis | Risk Management | Planning | Tool/Technique | T001 | Expert judgment | 36
Perform Qualitative Risk Analysis | Risk Management | Planning | Tool/Technique | T002 | Data gathering | 13
Perform Qualitative Risk Analysis | Risk Management | Planning | Tool/Technique | T005 | Data analysis | 32
Perform Qualitative Risk Analysis | Risk Management | Planning | Tool/Technique | T003 | Interpersonal and team skills | 21
Perform Qualitative Risk Analysis | Risk Management | Planning | Tool/Technique | T037 | Risk categorization | 1
Perform Qualitative Risk Analysis | Risk Management | Planning | Tool/Technique | T006 | Data representation | 11
Perform Qualitative Risk Analysis | Risk Management | Planning | Tool/Technique | T004 | Meetings | 28
Perform Qualitative Risk Analysis | Risk Management | Planning | Output | O006 | Project documents updates | 39
Perform Quantitative Risk Analysis | Risk Management | Planning | Input | I008 | Project management plan | 47
Perform Quantitative Risk Analysis | Risk Management | Planning | Input | I009 | Project documents | 43
Perform Quantitative Risk Analysis | Risk Management | Planning | Input | I004 | Enterprise environmental factors | 40
Perform Quantitative Risk Analysis | Risk Management | Planning | Input | I005 | Organizational process assets | 46
Perform Quantitative Risk Analysis | Risk Management | Planning | Tool/Technique | T001 | Expert judgment | 36
Perform Quantitative Risk Analysis | Risk Management | Planning | Tool/Technique | T002 | Data gathering | 13
Perform Quantitative Risk Analysis | Risk Management | Planning | Tool/Technique | T003 | Interpersonal and team skills | 21
Perform Quantitative Risk Analysis | Risk Management | Planning | Tool/Technique | T038 | Representations of uncertainty | 1
Perform Quantitative Risk Analysis | Risk Management | Planning | Tool/Technique | T005 | Data analysis | 32
Perform Quantitative Risk Analysis | Risk Management | Planning | Output | O006 | Project documents updates | 39
Plan Risk Responses | Risk Management | Planning | Input | I008 | Project management plan | 47
Plan Risk Responses | Risk Management | Planning | Input | I009 | Project documents | 43
Plan Risk Responses | Risk Management | Planning | Input | I004 | Enterprise environmental factors | 40
Plan Risk Responses | Risk Management | Planning | Input | I005 | Organizational process assets | 46
Plan Risk Responses | Risk Management | Planning | Tool/Technique | T001 | Expert judgment | 36
Plan Risk Responses | Risk Management | Planning | Tool/Technique | T002 | Data gathering | 13
Plan Risk Responses | Risk Management | Planning | Tool/Technique | T003 | Interpersonal and team skills | 21
Plan Risk Responses | Risk Management | Planning | Tool/Technique | T039 | Strategies for threats | 1
Plan Risk Responses | Risk Management | Planning | Tool/Technique | T040 | Strategies for opportunities | 1
Plan Risk Responses | Risk Management | Planning | Tool/Technique | T041 | Contingent response strategies | 1
Plan Risk Responses | Risk Management | Planning | Tool/Technique | T042 | Strategies for overall project risk | 1
Plan Risk Responses | Risk Management | Planning | Tool/Technique | T005 | Data analysis | 32
Plan Risk Responses | Risk Management | Planning | Tool/Technique | T007 | Decision making | 13
Plan Risk Responses | Risk Management | Planning | Output | O004 | Change requests | 24
Plan Risk Responses | Risk Management | Planning | Output | O005 | Project management plan updates | 26
Plan Risk Responses | Risk Management | Planning | Output | O006 | Project documents updates | 39
Plan Procurement Management | Procurement Management | Planning | Input | I006 | Project charter | 14
Plan Procurement Management | Procurement Management | Planning | Input | I007 | Business documents | 5
Plan Procurement Management | Procurement Management | Planning | Input | I008 | Project management plan | 47
Plan Procurement Management | Procurement Management | Planning | Input | I009 | Project documents | 43
Plan Procurement Management | Procurement Management | Planning | Input | I004 | Enterprise environmental factors | 40
Plan Procurement Management | Procurement Management | Planning | Input | I005 | Organizational process assets | 46
Plan Procurement Management | Procurement Management | Planning | Tool/Technique | T001 | Expert judgment | 36
Plan Procurement Management | Procurement Management | Planning | Tool/Technique | T002 | Data gathering | 13
Plan Procurement Management | Procurement Management | Planning | Tool/Technique | T005 | Data analysis | 32
Plan Procurement Management | Procurement Management | Planning | Tool/Technique | T043 | Source selection analysis | 1
Plan Procurement Management | Procurement Management | Planning | Tool/Technique | T004 | Meetings | 28
Plan Procurement Management | Procurement Management | Planning | Output | O039 | Procurement management plan | 1
Plan Procurement Management | Procurement Management | Planning | Output | O040 | Procurement strategy | 1
Plan Procurement Management | Procurement Management | Planning | Output | O041 | Bid documents | 1
Plan Procurement Management | Procurement Management | Planning | Output | O042 | Procurement statement of work | 1
Plan Procurement Management | Procurement Management | Planning | Output | O043 | Source selection criteria | 1
Plan Procurement Management | Procurement Management | Planning | Output | O044 | Make-or-buy decisions | 1
Plan Procurement Management | Procurement Management | Planning | Output | O045 | Independent cost estimates | 1
Plan Procurement Management | Procurement Management | Planning | Output | O004 | Change requests | 24
Plan Procurement Management | Procurement Management | Planning | Output | O006 | Project documents updates | 39
Plan Procurement Management | Procurement Management | Planning | Output | O046 | Organizational process assets updates | 10
Plan Stakeholder Engagement | Stakeholder Management | Planning | Input | I006 | Project charter | 14
Plan Stakeholder Engagement | Stakeholder Management | Planning | Input | I008 | Project management plan | 47
Plan Stakeholder Engagement | Stakeholder Management | Planning | Input | I009 | Project documents | 43
Plan Stakeholder Engagement | Stakeholder Management | Planning | Input | I003 | Agreements | 11
Plan Stakeholder Engagement | Stakeholder Management | Planning | Input | I004 | Enterprise environmental factors | 40
Plan Stakeholder Engagement | Stakeholder Management | Planning | Input | I005 | Organizational process assets | 46
Plan Stakeholder Engagement | Stakeholder Management | Planning | Tool/Technique | T001 | Expert judgment | 36
Plan Stakeholder Engagement | Stakeholder Management | Planning | Tool/Technique | T002 | Data gathering | 13
Plan Stakeholder Engagement | Stakeholder Management | Planning | Tool/Technique | T005 | Data analysis | 32
Plan Stakeholder Engagement | Stakeholder Management | Planning | Tool/Technique | T007 | Decision making | 13
Plan Stakeholder Engagement | Stakeholder Management | Planning | Tool/Technique | T006 | Data representation | 11
Plan Stakeholder Engagement | Stakeholder Management | Planning | Tool/Technique | T004 | Meetings | 28
Plan Stakeholder Engagement | Stakeholder Management | Planning | Output | O047 | Stakeholder engagement plan | 1
Direct and Manage Project Work | Integration Management | Executing | Input | I008 | Project management plan | 47
Direct and Manage Project Work | Integration Management | Executing | Input | I009 | Project documents | 43
Direct and Manage Project Work | Integration Management | Executing | Input | I012 | Approved change requests | 3
Direct and Manage Project Work | Integration Management | Executing | Input | I004 | Enterprise environmental factors | 40
Direct and Manage Project Work | Integration Management | Executing | Input | I005 | Organizational process assets | 46
Direct and Manage Project Work | Integration Management | Executing | Tool/Technique | T001 | Expert judgment | 36
Direct and Manage Project Work | Integration Management | Executing | Tool/Technique | T016 | Project management information system | 13
Direct and Manage Project Work | Integration Management | Executing | Tool/Technique | T004 | Meetings | 28
Direct and Manage Project Work | Integration Management | Executing | Output | O048 | Deliverables | 1
Direct and Manage Project Work | Integration Management | Executing | Output | O049 | Work performance data | 1
Direct and Manage Project Work | Integration Management | Executing | Output | O050 | Issue log | 1
Direct and Manage Project Work | Integration Management | Executing | Output | O004 | Change requests | 24
Direct and Manage Project Work | Integration Management | Executing | Output | O005 | Project management plan updates | 26
Direct and Manage Project Work | Integration Management | Executing | Output | O006 | Project documents updates | 39
Direct and Manage Project Work | Integration Management | Executing | Output | O046 | Organizational process assets updates | 10
Manage Project Knowledge | Integration Management | Executing | Input | I008 | Project management plan | 47
Manage Project Knowledge | Integration Management | Executing | Input | I009 | Project documents | 43
Manage Project Knowledge | Integration Management | Executing | Input | I013 | Deliverables | 2
Manage Project Knowledge | Integration Management | Executing | Input | I004 | Enterprise environmental factors | 40
Manage Project Knowledge | Integration Management | Executing | Input | I005 | Organizational process assets | 46
Manage Project Knowledge | Integration Management | Executing | Tool/Technique | T001 | Expert judgment | 36
Manage Project Knowledge | Integration Management | Executing | Tool/Technique | T044 | Knowledge management | 1
Manage Project Knowledge | Integration Management | Executing | Tool/Technique | T045 | Information management | 1
Manage Project Knowledge | Integration Management | Executing | Tool/Technique | T003 | Interpersonal and team skills | 21
Manage Project Knowledge | Integration Management | Executing | Output | O051 | Lessons learned register | 1
Manage Project Knowledge | Integration Management | Executing | Output | O005 | Project management plan updates | 26
Manage Project Knowledge | Integration Management | Executing | Output | O046 | Organizational process assets updates | 10
Manage Quality | Quality Management | Executing | Input | I008 | Project management plan | 47
Manage Quality | Quality Management | Executing | Input | I009 | Project documents | 43
Manage Quality | Quality Management | Executing | Input | I005 | Organizational process assets | 46
Manage Quality | Quality Management | Executing | Tool/Technique | T002 | Data gathering | 13
Manage Quality | Quality Management | Executing | Tool/Technique | T005 | Data analysis | 32
Manage Quality | Quality Management | Executing | Tool/Technique | T007 | Decision making | 13
Manage Quality | Quality Management | Executing | Tool/Technique | T006 | Data representation | 11
Manage Quality | Quality Management | Executing | Tool/Technique | T046 | Audits | 3
Manage Quality | Quality Management | Executing | Tool/Technique | T047 | Design for X | 1
Manage Quality | Quality Management | Executing | Tool/Technique | T048 | Problem solving | 2
Manage Quality | Quality Management | Executing | Tool/Technique | T049 | Quality improvement methods | 1
Manage Quality | Quality Management | Executing | Output | O052 | Quality reports | 1
Manage Quality | Quality Management | Executing | Output | O053 | Test and evaluation documents | 1
Manage Quality | Quality Management | Executing | Output | O004 | Change requests | 24
Manage Quality | Quality Management | Executing | Output | O005 | Project management plan updates | 26
Manage Quality | Quality Management | Executing | Output | O006 | Project documents updates | 39
Acquire Resources | Resource Management | Executing | Input | I008 | Project management plan | 47
Acquire Resources | Resource Management | Executing | Input | I009 | Project documents | 43
Acquire Resources | Resource Management | Executing | Input | I004 | Enterprise environmental factors | 40
Acquire Resources | Resource Management | Executing | Input | I005 | Organizational process assets | 46
Acquire Resources | Resource Management | Executing | Tool/Technique | T007 | Decision making | 13
Acquire Resources | Resource Management | Executing | Tool/Technique | T003 | Interpersonal and team skills | 21
Acquire Resources | Resource Management | Executing | Tool/Technique | T050 | Pre-assignment | 1
Acquire Resources | Resource Management | Executing | Tool/Technique | T051 | Virtual teams | 2
Acquire Resources | Resource Management | Executing | Output | O054 | Physical resource assignments | 1
Acquire Resources | Resource Management | Executing | Output | O055 | Project team assignments | 1
Acquire Resources | Resource Management | Executing | Output | O056 | Resource calendars | 1
Acquire Resources | Resource Management | Executing | Output | O004 | Change requests | 24
Acquire Resources | Resource Management | Executing | Output | O005 | Project management plan updates | 26
Acquire Resources | Resource Management | Executing | Output | O006 | Project documents updates | 39
Acquire Resources | Resource Management | Executing | Output | O057 | Enterprise environmental factors updates | 3
Acquire Resources | Resource Management | Executing | Output | O046 | Organizational process assets updates | 10
Develop Team | Resource Management | Executing | Input | I008 | Project management plan | 47
Develop Team | Resource Management | Executing | Input | I009 | Project documents | 43
Develop Team | Resource Management | Executing | Input | I004 | Enterprise environmental factors | 40
Develop Team | Resource Management | Executing | Input | I005 | Organizational process assets | 46
Develop Team | Resource Management | Executing | Tool/Technique | T052 | Colocation | 1
Develop Team | Resource Management | Executing | Tool/Technique | T051 | Virtual teams | 2
Develop Team | Resource Management | Executing | Tool/Technique | T033 | Communication technology | 3
Develop Team | Resource Management | Executing | Tool/Technique | T003 | Interpersonal and team skills | 21
Develop Team | Resource Management | Executing | Tool/Technique | T053 | Recognition and rewards | 1
Develop Team | Resource Management | Executing | Tool/Technique | T054 | Training | 1
Develop Team | Resource Management | Executing | Tool/Technique | T055 | Individual and team assessments | 1
Develop Team | Resource Management | Executing | Tool/Technique | T004 | Meetings | 28
Develop Team | Resource Management | Executing | Output | O058 | Team performance assessments | 1
Develop Team | Resource Management | Executing | Output | O004 | Change requests | 24
Develop Team | Resource Management | Executing | Output | O005 | Project management plan updates | 26
Develop Team | Resource Management | Executing | Output | O006 | Project documents updates | 39
Develop Team | Resource Management | Executing | Output | O057 | Enterprise environmental factors updates | 3
Develop Team | Resource Management | Executing | Output | O046 | Organizational process assets updates | 10
Manage Team | Resource Management | Executing | Input | I008 | Project management plan | 47
Manage Team | Resource Management | Executing | Input | I009 | Project documents | 43
Manage Team | Resource Management | Executing | Input | I014 | Work performance reports | 6
Manage Team | Resource Management | Executing | Input | I015 | Team performance assessments | 1
Manage Team | Resource Management | Executing | Input | I004 | Enterprise environmental factors | 40
Manage Team | Resource Management | Executing | Input | I005 | Organizational process assets | 46
Manage Team | Resource Management | Executing | Tool/Technique | T003 | Interpersonal and team skills | 21
Manage Team | Resource Management | Executing | Tool/Technique | T016 | Project management information system | 13
Manage Team | Resource Management | Executing | Output | O004 | Change requests | 24
Manage Team | Resource Management | Executing | Output | O005 | Project management plan updates | 26
Manage Team | Resource Management | Executing | Output | O006 | Project documents updates | 39
Manage Team | Resource Management | Executing | Output | O057 | Enterprise environmental factors updates | 3
Manage Communications | Communications Management | Executing | Input | I008 | Project management plan | 47
Manage Communications | Communications Management | Executing | Input | I009 | Project documents | 43
Manage Communications | Communications Management | Executing | Input | I014 | Work performance reports | 6
Manage Communications | Communications Management | Executing | Input | I004 | Enterprise environmental factors | 40
Manage Communications | Communications Management | Executing | Input | I005 | Organizational process assets | 46
Manage Communications | Communications Management | Executing | Tool/Technique | T033 | Communication technology | 3
Manage Communications | Communications Management | Executing | Tool/Technique | T035 | Communication methods | 2
Manage Communications | Communications Management | Executing | Tool/Technique | T056 | Communication skills | 2
Manage Communications | Communications Management | Executing | Tool/Technique | T016 | Project management information system | 13
Manage Communications | Communications Management | Executing | Tool/Technique | T057 | Project reporting | 1
Manage Communications | Communications Management | Executing | Tool/Technique | T003 | Interpersonal and team skills | 21
Manage Communications | Communications Management | Executing | Tool/Technique | T004 | Meetings | 28
Manage Communications | Communications Management | Executing | Output | O059 | Project communications | 1
Manage Communications | Communications Management | Executing | Output | O005 | Project management plan updates | 26
Manage Communications | Communications Management | Executing | Output | O006 | Project documents updates | 39
Manage Communications | Communications Management | Executing | Output | O046 | Organizational process assets updates | 10
Implement Risk Responses | Risk Management | Executing | Input | I008 | Project management plan | 47
Implement Risk Responses | Risk Management | Executing | Input | I009 | Project documents | 43
Implement Risk Responses | Risk Management | Executing | Input | I016 | Change requests | 2
Implement Risk Responses | Risk Management | Executing | Tool/Technique | T001 | Expert judgment | 36
Implement Risk Responses | Risk Management | Executing | Tool/Technique | T003 | Interpersonal and team skills | 21
Implement Risk Responses | Risk Management | Executing | Tool/Technique | T016 | Project management information system | 13
Implement Risk Responses | Risk Management | Executing | Output | O004 | Change requests | 24
Implement Risk Responses | Risk Management | Executing | Output | O006 | Project documents updates | 39
Conduct Procurements | Procurement Management | Executing | Input | I008 | Project management plan | 47
Conduct Procurements | Procurement Management | Executing | Input | I009 | Project documents | 43
Conduct Procurements | Procurement Management | Executing | Input | I011 | Procurement documentation | 4
Conduct Procurements | Procurement Management | Executing | Input | I017 | Seller proposals | 1
Conduct Procurements | Procurement Management | Executing | Input | I004 | Enterprise environmental factors | 40
Conduct Procurements | Procurement Management | Executing | Input | I005 | Organizational process assets | 46
Conduct Procurements | Procurement Management | Executing | Tool/Technique | T001 | Expert judgment | 36
Conduct Procurements | Procurement Management | Executing | Tool/Technique | T058 | Advertising | 1
Conduct Procurements | Procurement Management | Executing | Tool/Technique | T059 | Bidder conferences | 1
Conduct Procurements | Procurement Management | Executing | Tool/Technique | T005 | Data analysis | 32
Conduct Procurements | Procurement Management | Executing | Tool/Technique | T003 | Interpersonal and team skills | 21
Conduct Procurements | Procurement Management | Executing | Output | O060 | Selected sellers | 1
Conduct Procurements | Procurement Management | Executing | Output | O061 | Agreements | 1
Conduct Procurements | Procurement Management | Executing | Output | O004 | Change requests | 24
Conduct Procurements | Procurement Management | Executing | Output | O005 | Project management plan updates | 26
Conduct Procurements | Procurement Management | Executing | Output | O006 | Project documents updates | 39
Conduct Procurements | Procurement Management | Executing | Output | O046 | Organizational process assets updates | 10
Manage Stakeholder Engagement | Stakeholder Management | Executing | Input | I008 | Project management plan | 47
Manage Stakeholder Engagement | Stakeholder Management | Executing | Input | I009 | Project documents | 43
Manage Stakeholder Engagement | Stakeholder Management | Executing | Input | I014 | Work performance reports | 6
Manage Stakeholder Engagement | Stakeholder Management | Executing | Input | I004 | Enterprise environmental factors | 40
Manage Stakeholder Engagement | Stakeholder Management | Executing | Input | I005 | Organizational process assets | 46
Manage Stakeholder Engagement | Stakeholder Management | Executing | Tool/Technique | T001 | Expert judgment | 36
Manage Stakeholder Engagement | Stakeholder Management | Executing | Tool/Technique | T056 | Communication skills | 2
Manage Stakeholder Engagement | Stakeholder Management | Executing | Tool/Technique | T003 | Interpersonal and team skills | 21
Manage Stakeholder Engagement | Stakeholder Management | Executing | Tool/Technique | T060 | Ground rules | 1
Manage Stakeholder Engagement | Stakeholder Management | Executing | Tool/Technique | T004 | Meetings | 28
Manage Stakeholder Engagement | Stakeholder Management | Executing | Output | O004 | Change requests | 24
Manage Stakeholder Engagement | Stakeholder Management | Executing | Output | O005 | Project management plan updates | 26
Manage Stakeholder Engagement | Stakeholder Management | Executing | Output | O006 | Project documents updates | 39
Manage Stakeholder Engagement | Stakeholder Management | Executing | Output | O046 | Organizational process assets updates | 10
Monitor and Control Project Work | Integration Management | Monitoring & Controlling | Input | I008 | Project management plan | 47
Monitor and Control Project Work | Integration Management | Monitoring & Controlling | Input | I009 | Project documents | 43
Monitor and Control Project Work | Integration Management | Monitoring & Controlling | Input | I018 | Work performance information | 1
Monitor and Control Project Work | Integration Management | Monitoring & Controlling | Input | I003 | Agreements | 11
Monitor and Control Project Work | Integration Management | Monitoring & Controlling | Input | I004 | Enterprise environmental factors | 40
Monitor and Control Project Work | Integration Management | Monitoring & Controlling | Input | I005 | Organizational process assets | 46
Monitor and Control Project Work | Integration Management | Monitoring & Controlling | Tool/Technique | T001 | Expert judgment | 36
Monitor and Control Project Work | Integration Management | Monitoring & Controlling | Tool/Technique | T005 | Data analysis | 32
Monitor and Control Project Work | Integration Management | Monitoring & Controlling | Tool/Technique | T007 | Decision making | 13
Monitor and Control Project Work | Integration Management | Monitoring & Controlling | Tool/Technique | T004 | Meetings | 28
Monitor and Control Project Work | Integration Management | Monitoring & Controlling | Output | O062 | Work performance reports | 1
Monitor and Control Project Work | Integration Management | Monitoring & Controlling | Output | O004 | Change requests | 24
Monitor and Control Project Work | Integration Management | Monitoring & Controlling | Output | O005 | Project management plan updates | 26
Monitor and Control Project Work | Integration Management | Monitoring & Controlling | Output | O006 | Project documents updates | 39
Perform Integrated Change Control | Integration Management | Monitoring & Controlling | Input | I008 | Project management plan | 47
Perform Integrated Change Control | Integration Management | Monitoring & Controlling | Input | I009 | Project documents | 43
Perform Integrated Change Control | Integration Management | Monitoring & Controlling | Input | I014 | Work performance reports | 6
Perform Integrated Change Control | Integration Management | Monitoring & Controlling | Input | I016 | Change requests | 2
Perform Integrated Change Control | Integration Management | Monitoring & Controlling | Input | I004 | Enterprise environmental factors | 40
Perform Integrated Change Control | Integration Management | Monitoring & Controlling | Input | I005 | Organizational process assets | 46
Perform Integrated Change Control | Integration Management | Monitoring & Controlling | Tool/Technique | T001 | Expert judgment | 36
Perform Integrated Change Control | Integration Management | Monitoring & Controlling | Tool/Technique | T061 | Change control tools | 1
Perform Integrated Change Control | Integration Management | Monitoring & Controlling | Tool/Technique | T005 | Data analysis | 32
Perform Integrated Change Control | Integration Management | Monitoring & Controlling | Tool/Technique | T007 | Decision making | 13
Perform Integrated Change Control | Integration Management | Monitoring & Controlling | Tool/Technique | T004 | Meetings | 28
Perform Integrated Change Control | Integration Management | Monitoring & Controlling | Output | O063 | Approved change requests | 1
Perform Integrated Change Control | Integration Management | Monitoring & Controlling | Output | O005 | Project management plan updates | 26
Perform Integrated Change Control | Integration Management | Monitoring & Controlling | Output | O006 | Project documents updates | 39
Validate Scope | Scope Management | Monitoring & Controlling | Input | I008 | Project management plan | 47
Validate Scope | Scope Management | Monitoring & Controlling | Input | I009 | Project documents | 43
Validate Scope | Scope Management | Monitoring & Controlling | Input | I019 | Verified deliverables | 1
Validate Scope | Scope Management | Monitoring & Controlling | Input | I020 | Work performance data | 9
Validate Scope | Scope Management | Monitoring & Controlling | Tool/Technique | T062 | Inspection | 3
Validate Scope | Scope Management | Monitoring & Controlling | Tool/Technique | T007 | Decision making | 13
Validate Scope | Scope Management | Monitoring & Controlling | Output | O064 | Accepted deliverables | 1
Validate Scope | Scope Management | Monitoring & Controlling | Output | O065 | Work performance information | 10
Validate Scope | Scope Management | Monitoring & Controlling | Output | O004 | Change requests | 24
Validate Scope | Scope Management | Monitoring & Controlling | Output | O006 | Project documents updates | 39
Control Scope | Scope Management | Monitoring & Controlling | Input | I008 | Project management plan | 47
Control Scope | Scope Management | Monitoring & Controlling | Input | I009 | Project documents | 43
Control Scope | Scope Management | Monitoring & Controlling | Input | I020 | Work performance data | 9
Control Scope | Scope Management | Monitoring & Controlling | Input | I005 | Organizational process assets | 46
Control Scope | Scope Management | Monitoring & Controlling | Tool/Technique | T005 | Data analysis | 32
Control Scope | Scope Management | Monitoring & Controlling | Tool/Technique | T063 | Variance analysis | 1
Control Scope | Scope Management | Monitoring & Controlling | Output | O065 | Work performance information | 10
Control Scope | Scope Management | Monitoring & Controlling | Output | O004 | Change requests | 24
Control Scope | Scope Management | Monitoring & Controlling | Output | O005 | Project management plan updates | 26
Control Scope | Scope Management | Monitoring & Controlling | Output | O006 | Project documents updates | 39
Control Schedule | Schedule Management | Monitoring & Controlling | Input | I008 | Project management plan | 47
Control Schedule | Schedule Management | Monitoring & Controlling | Input | I009 | Project documents | 43
Control Schedule | Schedule Management | Monitoring & Controlling | Input | I020 | Work performance data | 9
Control Schedule | Schedule Management | Monitoring & Controlling | Input | I005 | Organizational process assets | 46
Control Schedule | Schedule Management | Monitoring & Controlling | Tool/Technique | T005 | Data analysis | 32
Control Schedule | Schedule Management | Monitoring & Controlling | Tool/Technique | T022 | Critical path method | 2
Control Schedule | Schedule Management | Monitoring & Controlling | Tool/Technique | T016 | Project management information system | 13
Control Schedule | Schedule Management | Monitoring & Controlling | Tool/Technique | T023 | Resource optimization | 2
Control Schedule | Schedule Management | Monitoring & Controlling | Tool/Technique | T015 | Leads and lags | 3
Control Schedule | Schedule Management | Monitoring & Controlling | Tool/Technique | T024 | Schedule compression | 2
Control Schedule | Schedule Management | Monitoring & Controlling | Output | O065 | Work performance information | 10
Control Schedule | Schedule Management | Monitoring & Controlling | Output | O066 | Schedule forecasts | 1
Control Schedule | Schedule Management | Monitoring & Controlling | Output | O004 | Change requests | 24
Control Schedule | Schedule Management | Monitoring & Controlling | Output | O005 | Project management plan updates | 26
Control Schedule | Schedule Management | Monitoring & Controlling | Output | O006 | Project documents updates | 39
Control Costs | Cost Management | Monitoring & Controlling | Input | I008 | Project management plan | 47
Control Costs | Cost Management | Monitoring & Controlling | Input | I009 | Project documents | 43
Control Costs | Cost Management | Monitoring & Controlling | Input | I021 | Project funding requirements | 1
Control Costs | Cost Management | Monitoring & Controlling | Input | I020 | Work performance data | 9
Control Costs | Cost Management | Monitoring & Controlling | Input | I005 | Organizational process assets | 46
Control Costs | Cost Management | Monitoring & Controlling | Tool/Technique | T001 | Expert judgment | 36
Control Costs | Cost Management | Monitoring & Controlling | Tool/Technique | T005 | Data analysis | 32
Control Costs | Cost Management | Monitoring & Controlling | Tool/Technique | T064 | To-complete performance index | 1
Control Costs | Cost Management | Monitoring & Controlling | Tool/Technique | T016 | Project management information system | 13
Control Costs | Cost Management | Monitoring & Controlling | Output | O065 | Work performance information | 10
Control Costs | Cost Management | Monitoring & Controlling | Output | O067 | Cost forecasts | 1
Control Costs | Cost Management | Monitoring & Controlling | Output | O004 | Change requests | 24
Control Costs | Cost Management | Monitoring & Controlling | Output | O005 | Project management plan updates | 26
Control Costs | Cost Management | Monitoring & Controlling | Output | O006 | Project documents updates | 39
Control Quality | Quality Management | Monitoring & Controlling | Input | I008 | Project management plan | 47
Control Quality | Quality Management | Monitoring & Controlling | Input | I009 | Project documents | 43
Control Quality | Quality Management | Monitoring & Controlling | Input | I012 | Approved change requests | 3
Control Quality | Quality Management | Monitoring & Controlling | Input | I013 | Deliverables | 2
Control Quality | Quality Management | Monitoring & Controlling | Input | I020 | Work performance data | 9
Control Quality | Quality Management | Monitoring & Controlling | Input | I004 | Enterprise environmental factors | 40
Control Quality | Quality Management | Monitoring & Controlling | Input | I005 | Organizational process assets | 46
Control Quality | Quality Management | Monitoring & Controlling | Tool/Technique | T002 | Data gathering | 13
Control Quality | Quality Management | Monitoring & Controlling | Tool/Technique | T005 | Data analysis | 32
Control Quality | Quality Management | Monitoring & Controlling | Tool/Technique | T062 | Inspection | 3
Control Quality | Quality Management | Monitoring & Controlling | Tool/Technique | T065 | Testing/product evaluations | 1
Control Quality | Quality Management | Monitoring & Controlling | Tool/Technique | T006 | Data representation | 11
Control Quality | Quality Management | Monitoring & Controlling | Tool/Technique | T004 | Meetings | 28
Control Quality | Quality Management | Monitoring & Controlling | Output | O068 | Quality control measurements | 1
Control Quality | Quality Management | Monitoring & Controlling | Output | O069 | Verified deliverables | 1
Control Quality | Quality Management | Monitoring & Controlling | Output | O065 | Work performance information | 10
Control Quality | Quality Management | Monitoring & Controlling | Output | O004 | Change requests | 24
Control Quality | Quality Management | Monitoring & Controlling | Output | O005 | Project management plan updates | 26
Control Quality | Quality Management | Monitoring & Controlling | Output | O006 | Project documents updates | 39
Control Resources | Resource Management | Monitoring & Controlling | Input | I008 | Project management plan | 47
Control Resources | Resource Management | Monitoring & Controlling | Input | I009 | Project documents | 43
Control Resources | Resource Management | Monitoring & Controlling | Input | I020 | Work performance data | 9
Control Resources | Resource Management | Monitoring & Controlling | Input | I003 | Agreements | 11
Control Resources | Resource Management | Monitoring & Controlling | Input | I005 | Organizational process assets | 46
Control Resources | Resource Management | Monitoring & Controlling | Tool/Technique | T005 | Data analysis | 32
Control Resources | Resource Management | Monitoring & Controlling | Tool/Technique | T048 | Problem solving | 2
Control Resources | Resource Management | Monitoring & Controlling | Tool/Technique | T003 | Interpersonal and team skills | 21
Control Resources | Resource Management | Monitoring & Controlling | Tool/Technique | T016 | Project management information system | 13
Control Resources | Resource Management | Monitoring & Controlling | Output | O065 | Work performance information | 10
Control Resources | Resource Management | Monitoring & Controlling | Output | O004 | Change requests | 24
Control Resources | Resource Management | Monitoring & Controlling | Output | O005 | Project management plan updates | 26
Control Resources | Resource Management | Monitoring & Controlling | Output | O006 | Project documents updates | 39
Monitor Communications | Communications Management | Monitoring & Controlling | Input | I008 | Project management plan | 47
Monitor Communications | Communications Management | Monitoring & Controlling | Input | I009 | Project documents | 43
Monitor Communications | Communications Management | Monitoring & Controlling | Input | I020 | Work performance data | 9
Monitor Communications | Communications Management | Monitoring & Controlling | Input | I004 | Enterprise environmental factors | 40
Monitor Communications | Communications Management | Monitoring & Controlling | Input | I005 | Organizational process assets | 46
Monitor Communications | Communications Management | Monitoring & Controlling | Tool/Technique | T001 | Expert judgment | 36
Monitor Communications | Communications Management | Monitoring & Controlling | Tool/Technique | T016 | Project management information system | 13
Monitor Communications | Communications Management | Monitoring & Controlling | Tool/Technique | T006 | Data representation | 11
Monitor Communications | Communications Management | Monitoring & Controlling | Tool/Technique | T003 | Interpersonal and team skills | 21
Monitor Communications | Communications Management | Monitoring & Controlling | Tool/Technique | T004 | Meetings | 28
Monitor Communications | Communications Management | Monitoring & Controlling | Output | O065 | Work performance information | 10
Monitor Communications | Communications Management | Monitoring & Controlling | Output | O004 | Change requests | 24
Monitor Communications | Communications Management | Monitoring & Controlling | Output | O005 | Project management plan updates | 26
Monitor Communications | Communications Management | Monitoring & Controlling | Output | O006 | Project documents updates | 39
Monitor Risks | Risk Management | Monitoring & Controlling | Input | I008 | Project management plan | 47
Monitor Risks | Risk Management | Monitoring & Controlling | Input | I009 | Project documents | 43
Monitor Risks | Risk Management | Monitoring & Controlling | Input | I020 | Work performance data | 9
Monitor Risks | Risk Management | Monitoring & Controlling | Input | I014 | Work performance reports | 6
Monitor Risks | Risk Management | Monitoring & Controlling | Tool/Technique | T005 | Data analysis | 32
Monitor Risks | Risk Management | Monitoring & Controlling | Tool/Technique | T046 | Audits | 3
Monitor Risks | Risk Management | Monitoring & Controlling | Tool/Technique | T004 | Meetings | 28
Monitor Risks | Risk Management | Monitoring & Controlling | Output | O065 | Work performance information | 10
Monitor Risks | Risk Management | Monitoring & Controlling | Output | O004 | Change requests | 24
Monitor Risks | Risk Management | Monitoring & Controlling | Output | O005 | Project management plan updates | 26
Monitor Risks | Risk Management | Monitoring & Controlling | Output | O006 | Project documents updates | 39
Control Procurements | Procurement Management | Monitoring & Controlling | Input | I008 | Project management plan | 47
Control Procurements | Procurement Management | Monitoring & Controlling | Input | I009 | Project documents | 43
Control Procurements | Procurement Management | Monitoring & Controlling | Input | I003 | Agreements | 11
Control Procurements | Procurement Management | Monitoring & Controlling | Input | I011 | Procurement documentation | 4
Control Procurements | Procurement Management | Monitoring & Controlling | Input | I012 | Approved change requests | 3
Control Procurements | Procurement Management | Monitoring & Controlling | Input | I014 | Work performance reports | 6
Control Procurements | Procurement Management | Monitoring & Controlling | Input | I004 | Enterprise environmental factors | 40
Control Procurements | Procurement Management | Monitoring & Controlling | Input | I005 | Organizational process assets | 46
Control Procurements | Procurement Management | Monitoring & Controlling | Tool/Technique | T001 | Expert judgment | 36
Control Procurements | Procurement Management | Monitoring & Controlling | Tool/Technique | T066 | Claims administration | 1
Control Procurements | Procurement Management | Monitoring & Controlling | Tool/Technique | T005 | Data analysis | 32
Control Procurements | Procurement Management | Monitoring & Controlling | Tool/Technique | T062 | Inspection | 3
Control Procurements | Procurement Management | Monitoring & Controlling | Tool/Technique | T046 | Audits | 3
Control Procurements | Procurement Management | Monitoring & Controlling | Output | O070 | Closed procurements | 1
Control Procurements | Procurement Management | Monitoring & Controlling | Output | O065 | Work performance information | 10
Control Procurements | Procurement Management | Monitoring & Controlling | Output | O071 | Procurement documentation updates | 1
Control Procurements | Procurement Management | Monitoring & Controlling | Output | O004 | Change requests | 24
Control Procurements | Procurement Management | Monitoring & Controlling | Output | O005 | Project management plan updates | 26
Control Procurements | Procurement Management | Monitoring & Controlling | Output | O006 | Project documents updates | 39
Control Procurements | Procurement Management | Monitoring & Controlling | Output | O046 | Organizational process assets updates | 10
Monitor Stakeholder Engagement | Stakeholder Management | Monitoring & Controlling | Input | I008 | Project management plan | 47
Monitor Stakeholder Engagement | Stakeholder Management | Monitoring & Controlling | Input | I009 | Project documents | 43
Monitor Stakeholder Engagement | Stakeholder Management | Monitoring & Controlling | Input | I020 | Work performance data | 9
Monitor Stakeholder Engagement | Stakeholder Management | Monitoring & Controlling | Input | I004 | Enterprise environmental factors | 40
Monitor Stakeholder Engagement | Stakeholder Management | Monitoring & Controlling | Input | I005 | Organizational process assets | 46
Monitor Stakeholder Engagement | Stakeholder Management | Monitoring & Controlling | Tool/Technique | T001 | Expert judgment | 36
Monitor Stakeholder Engagement | Stakeholder Management | Monitoring & Controlling | Tool/Technique | T016 | Project management information system | 13
Monitor Stakeholder Engagement | Stakeholder Management | Monitoring & Controlling | Tool/Technique | T005 | Data analysis | 32
Monitor Stakeholder Engagement | Stakeholder Management | Monitoring & Controlling | Tool/Technique | T007 | Decision making | 13
Monitor Stakeholder Engagement | Stakeholder Management | Monitoring & Controlling | Tool/Technique | T006 | Data representation | 11
Monitor Stakeholder Engagement | Stakeholder Management | Monitoring & Controlling | Tool/Technique | T003 | Interpersonal and team skills | 21
Monitor Stakeholder Engagement | Stakeholder Management | Monitoring & Controlling | Tool/Technique | T004 | Meetings | 28
Monitor Stakeholder Engagement | Stakeholder Management | Monitoring & Controlling | Output | O065 | Work performance information | 10
Monitor Stakeholder Engagement | Stakeholder Management | Monitoring & Controlling | Output | O004 | Change requests | 24
Monitor Stakeholder Engagement | Stakeholder Management | Monitoring & Controlling | Output | O005 | Project management plan updates | 26
Monitor Stakeholder Engagement | Stakeholder Management | Monitoring & Controlling | Output | O006 | Project documents updates | 39
Close Project or Phase | Integration Management | Closing | Input | I006 | Project charter | 14
Close Project or Phase | Integration Management | Closing | Input | I008 | Project management plan | 47
Close Project or Phase | Integration Management | Closing | Input | I009 | Project documents | 43
Close Project or Phase | Integration Management | Closing | Input | I022 | Accepted deliverables | 1
Close Project or Phase | Integration Management | Closing | Input | I007 | Business documents | 5
Close Project or Phase | Integration Management | Closing | Input | I003 | Agreements | 11
Close Project or Phase | Integration Management | Closing | Input | I011 | Procurement documentation | 4
Close Project or Phase | Integration Management | Closing | Input | I005 | Organizational process assets | 46
Close Project or Phase | Integration Management | Closing | Tool/Technique | T001 | Expert judgment | 36
Close Project or Phase | Integration Management | Closing | Tool/Technique | T005 | Data analysis | 32
Close Project or Phase | Integration Management | Closing | Tool/Technique | T004 | Meetings | 28
Close Project or Phase | Integration Management | Closing | Output | O006 | Project documents updates | 39
Close Project or Phase | Integration Management | Closing | Output | O072 | Final product/service/result transition | 1
Close Project or Phase | Integration Management | Closing | Output | O073 | Final report | 1
Close Project or Phase | Integration Management | Closing | Output | O046 | Organizational process assets updates | 10
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## CH9 Project Quality Management
Questions | Answers
1 | A
2 | C
3 | C
4 | A
5 | C
6 | D
7 | C
8 | C
9 | C
10 | A
11 | C
12 | C
13 | C
14 | B
15 | A
16 | B
17 | D
18 | B
19 | D
20 | A
21 | A
22 | A
23
24
25
26
27
28
29
30
| Score | 86.36%

## CH10 Project Resource Managemen
Questions | Answers |  | Rev
1 | D | TRUE
2 | B | FALSE | A
3 | D | TRUE
4 | A | TRUE
5 | B | TRUE
6 | D | TRUE
7 | A | TRUE
8 | A | TRUE
9 | C | TRUE
10 | C | TRUE
11 | D | TRUE
12 | B | TRUE
13 | A | TRUE
14 | C | TRUE
15 | B | FALSE | D
16 | D | TRUE
17 | D | TRUE
18 | B | TRUE
19 | A | TRUE
20 | A | FALSE | C
21 | A | FALSE | C
22 | D | TRUE
23 | B | TRUE
24 | C | FALSE | D
25 | B | TRUE
| Score | 80%

## CH10 Project Comms Manag
Questions | Answers |  | Rev
1 |  | FALSE
2 |  | FALSE
3 |  | FALSE
4 |  | FALSE
5 |  | FALSE
6 |  | FALSE
7 |  | FALSE
8 |  | FALSE
9 |  | FALSE
10 |  | FALSE
11 |  | FALSE
12 |  | FALSE
13 |  | FALSE
14 |  | FALSE
15 |  | FALSE
16 |  | FALSE
17 |  | FALSE
18 |  | FALSE
19 |  | FALSE
20 |  | FALSE
21 |  | FALSE
22 |  | FALSE
23 |  | FALSE
24 |  | FALSE
25 |  | FALSE
| Score | 0%