## Practice Problems
Earned Value Management - Practice Problems
Write your answers in Column F, then check the Solutions sheet
Difficulty: | Easy | Medium | Hard
# | Difficulty | Given Information | Question | Formula Hint | Your Answer
1 | Easy | BAC = $100,000 PV = $40,000 EV = $35,000 AC = $45,000 | Calculate the Schedule Variance (SV) | SV = EV - PV
2 | Easy | BAC = $100,000 PV = $40,000 EV = $35,000 AC = $45,000 | Calculate the Cost Variance (CV) | CV = EV - AC
3 | Easy | BAC = $100,000 PV = $40,000 EV = $35,000 AC = $45,000 | Calculate the Schedule Performance Index (SPI) | SPI = EV / PV
4 | Easy | BAC = $100,000 PV = $40,000 EV = $35,000 AC = $45,000 | Calculate the Cost Performance Index (CPI) | CPI = EV / AC
5 | Easy | EV = $50,000 PV = $60,000 | Is the project ahead or behind schedule? | If SV is negative...
6 | Easy | EV = $80,000 AC = $70,000 | Is the project over or under budget? | If CV is positive...
7 | Medium | BAC = $200,000 EV = $80,000 AC = $100,000 CPI = 0.80 | Calculate EAC assuming typical variance continues | EAC = BAC / CPI
8 | Medium | BAC = $150,000 EV = $60,000 AC = $75,000 | Calculate EAC assuming atypical (one-time) variance | EAC = AC + (BAC - EV)
9 | Medium | BAC = $500,000 EAC = $625,000 | Calculate the Variance at Completion (VAC) | VAC = BAC - EAC
10 | Medium | EAC = $180,000 AC = $120,000 | Calculate the Estimate to Complete (ETC) | ETC = EAC - AC
11 | Medium | BAC = $100,000 EV = $40,000 AC = $50,000 | Calculate TCPI to meet original budget (BAC) | TCPI = (BAC-EV)/(BAC-AC)
12 | Medium | SPI = 0.9 CPI = 0.85 Project is 50% complete | Which is the bigger problem - schedule or cost? | Lower index = worse
13 | Medium | CPI = 1.2 SPI = 0.8 | Describe the project status in plain English | CPI > 1 means... SPI < 1 means...
14 | Medium | CV = -$15,000 SV = $10,000 | Describe the project status in plain English | Negative CV means... Positive SV means...
15 | Medium | TCPI (BAC) = 1.25 | What does this tell you about the project? | TCPI > 1 means...
16 | Hard | BAC = $300,000 PV = $150,000 EV = $120,000 AC = $140,000 | Calculate EAC using CPI × SPI method | First find CPI & SPI EAC = AC + [(BAC-EV)/(CPI×SPI)]
17 | Hard | Project duration: 12 months BAC = $240,000 Month 6: EV = $100,000, AC = $130,000 Assuming linear spending | What was the Planned Value at Month 6? | Linear = equal monthly amounts
18 | Hard | BAC = $400,000 At 40% complete: EV = $160,000 AC = $200,000 | If typical variance continues, how much MORE money is needed to finish? | Find EAC, then ETC
19 | Hard | BAC = $500,000 EV = $200,000 AC = $250,000 EAC = $600,000 | Calculate both TCPI values (BAC and EAC based) | TCPI(BAC) and TCPI(EAC)
20 | Hard | A project has CPI = 0.75 and is 60% complete. BAC = $1,000,000 | What is the forecasted cost overrun at completion? | Find EAC, then VAC
21 | Hard | Your project shows: SPI = 1.1, CPI = 0.9 Management asks for status | Which statement is TRUE? A) Under budget, behind schedule B) Over budget, ahead of schedule C) Under budget, ahead of schedule D) Over budget, behind schedule | SPI > 1 = ahead CPI < 1 = over budget
22 | Hard | EAC = $275,000 BAC = $250,000 EV = $125,000 AC = $150,000 | To meet the NEW estimate (EAC), what efficiency is needed for remaining work? | TCPI based on EAC
23 | Hard | You have $80,000 remaining budget. Remaining work value = $100,000 | What TCPI do you need to finish on budget? | TCPI = Work remaining / $ remaining
24 | Hard | Project A: CPI = 0.95, SPI = 1.05 Project B: CPI = 1.10, SPI = 0.90 | Which project is in better overall health? Why? | Consider both metrics
25 | Hard | BAC = $800,000 6 months into 12-month project EV = $350,000 AC = $400,000 PV = $400,000 | Calculate: SV, CV, SPI, CPI, EAC (typical), VAC, and project status summary | Use all formulas

## Solutions
Earned Value Practice Problems - SOLUTIONS
Try to solve problems first before checking answers!
# | Answer | Calculation | Explanation
1 | SV = -$5,000 | 35,000 - 40,000 = -5,000 | Negative SV means behind schedule - earned less than planned
2 | CV = -$10,000 | 35,000 - 45,000 = -10,000 | Negative CV means over budget - spent more than earned
3 | SPI = 0.875 | 35,000 / 40,000 = 0.875 | SPI < 1 means only accomplishing 87.5% of planned work
4 | CPI = 0.778 | 35,000 / 45,000 = 0.778 | CPI < 1 means only getting $0.78 of value per $1 spent
5 | Behind schedule | SV = 50,000 - 60,000 = -10,000 | Negative SV = behind schedule (earned less than planned)
6 | Under budget | CV = 80,000 - 70,000 = +10,000 | Positive CV = under budget (earned more than spent)
7 | EAC = $250,000 | 200,000 / 0.80 = 250,000 | If CPI stays at 0.80, project will cost $250K (25% over)
8 | EAC = $165,000 | 75,000 + (150,000 - 60,000) = 165,000 | One-time issue: spent + remaining work at original rate
9 | VAC = -$125,000 | 500,000 - 625,000 = -125,000 | Project will be $125K over budget at completion
10 | ETC = $60,000 | 180,000 - 120,000 = 60,000 | Need $60K more to complete the project
11 | TCPI = 1.20 | (100,000-40,000)/(100,000-50,000) = 60,000/50,000 = 1.20 | Need 120% efficiency on remaining work to meet budget
12 | Cost is bigger problem | CPI (0.85) < SPI (0.90) | Lower CPI means cost performance is worse than schedule
13 | Under budget, behind schedule | CPI > 1 = under budget SPI < 1 = behind schedule | Getting good value for money but not completing work fast enough
14 | Over budget, ahead of schedule | CV negative = over budget SV positive = ahead of schedule | Completing work faster than planned but spending too much
15 | Need 25% more efficiency | TCPI 1.25 means must be 25% more efficient than current performance | Very difficult to achieve - may need to revise budget
16 | EAC = $364,583 | CPI = 120/140 = 0.857 SPI = 120/150 = 0.80 EAC = 140,000 + [(300,000-120,000)/(0.857×0.80)] = 140,000 + [180,000/0.686] = 140,000 + 262,391 = $402,391 | Using both indices gives most conservative estimate
17 | PV = $120,000 | Linear: $240,000 / 12 months = $20,000/month 6 months × $20,000 = $120,000 | At month 6, should have planned to spend half the budget
18 | ETC = $300,000 | CPI = 160,000/200,000 = 0.80 EAC = 400,000/0.80 = $500,000 ETC = 500,000 - 200,000 = $300,000 | Need $300K more, which is $100K over remaining budget
19 | TCPI(BAC)=1.20 TCPI(EAC)=0.86 | TCPI(BAC) = (500,000-200,000)/(500,000-250,000) = 300,000/250,000 = 1.20 TCPI(EAC) = (500,000-200,000)/(600,000-250,000) = 300,000/350,000 = 0.86 | Can't meet BAC (need 120%), but can meet EAC (only need 86%)
20 | VAC = -$333,333 | EAC = 1,000,000/0.75 = $1,333,333 VAC = 1,000,000 - 1,333,333 = -$333,333 | Project will be ~$333K over budget at completion
21 | B) Over budget, ahead of schedule | SPI 1.1 > 1 = ahead of schedule CPI 0.9 < 1 = over budget | Completing work faster but spending more than planned
22 | TCPI(EAC) = 0.92 | (250,000-125,000)/(275,000-150,000) = 125,000/125,000 = 1.0 | Need exactly current efficiency to meet new estimate
23 | TCPI = 1.25 | 100,000 / 80,000 = 1.25 | Need to be 25% more efficient than average to finish on budget
24 | Project A is healthier | A: Slightly over budget (CPI 0.95), ahead of schedule (SPI 1.05) B: Under budget but significantly behind schedule | Schedule delays often harder to recover; A's issues are minor
25 | Full Analysis Below | SV = 350K-400K = -$50K CV = 350K-400K = -$50K SPI = 350/400 = 0.875 CPI = 350/400 = 0.875 EAC = 800K/0.875 = $914,286 VAC = 800K-914K = -$114,286 | Project is 12.5% behind schedule AND 12.5% over budget. Will likely cost ~$114K more than planned.

## Formula Quick Ref
EV Formulas Quick Reference
VARIANCES (Negative = Bad)
SV (Schedule Variance) | EV - PV
CV (Cost Variance) | EV - AC
VAC (Variance at Completion) | BAC - EAC
INDICES (< 1.0 = Bad)
SPI (Schedule Performance Index) | EV / PV
CPI (Cost Performance Index) | EV / AC
FORECASTS
EAC (Atypical) | AC + (BAC - EV)
EAC (Typical) ★ MOST COMMON | BAC / CPI
EAC (SPI & CPI) | AC + [(BAC-EV)/(CPI×SPI)]
ETC (Estimate to Complete) | EAC - AC
TCPI
TCPI (meet BAC) | (BAC - EV) / (BAC - AC)
TCPI (meet EAC) | (BAC - EV) / (EAC - AC)